05-11 Internal Meeting_ Feasibility Study and Risk

发言人 1  00:00:03

Um, okay. Um, I hope everyone's okay. Uh, thanks for the information, Claire. We've just trying to review it at the moment. I'm not sure wh- whether we'll have the model updated for the skid set. Um,

发言人 1  00:00:15

Sizing and also the requirements for

发言人 2  00:00:18

the Peter because Peter's Peter has the one Peter is the one that had to run around and find the information for me. So we should thank Peter for this revised kid sizes.

发言人 1  00:00:28

Brilliant, I don't know Mark. Did you have chance to place them in?

发言人 2  00:00:31

I haven't not yet. No, I'm having a... Yeah,

发言人 1  00:00:33

yeah, we only...

发言人 2  00:00:34

We actually but.

发言人 3  00:00:36

I'll get on it as soon as my computer's working properly

发言人 1  00:00:38

, yeah. And then we can add those in just to check whether we've got better access around. We should have, but let's have a look at what sort of dimensions we have.

发言人 1  00:00:50

Um, so this week we're going to try to, um, finish off the feasibility study. I have tried to chase Mike, Claire, and I haven't heard anything back in terms of costs, um, from Coleman and James at the moment.

发言人 1  00:01:03

So, that's a bit of a risk, um, because they hold quite a lot of the costs in terms of the demolition and making good. that area, so I'm still chasing Mike on that, but I've put the session in for next week in terms of trying to feed out from the feasibility study on the Monday, so I've extended that session, but.

发言人 1  00:01:22

Can I keep in contact with you this week about whether I hear back from Cole Coleman and James on their cost? So I'll continue to chase them all week, but Mike's not around at the moment, so I haven't.

发言人 1  00:01:36

Yeah, and his contact, our contact is normally through him. So, okay, shall I jump onto the actions and you can discuss it or hopefully jog some of our discussions.

发言人 1  00:01:53

So the first action on the RFI is around the showers, so I haven't managed to get hold of Mike yet to discuss relocating the shower in that area, so yeah, I will try.

发言人 1  00:02:05

Contacting in terms of the HVAC work, I think Brian only got the drawings Thursday, Friday last week, so I'm not sure that he's managed to progress that, but I will chase him on that as well.

发言人 1  00:02:18

Um, and then the disposal route for the new waste tank. Uh, it's action on yourself, Claire, just to discuss internally with Asim and Ken.

发言人 1  00:02:28

and confirm. Do you want me to close it out? Because that's probably an internal discussion that.

发言人 2  00:02:34

Yeah, we put it on the risk register.

发言人 1  00:02:37

Okay，

发言人 2  00:02:38

but we don't lose it。

发言人 1  00:02:40

yeah, okay.

发言人 3  00:02:42

There's an assumption that there isn't an additional waste tank. It's just how we get it from that module into... Well,

发言人 2  00:02:47

no, it's more. Can we put it in our standard waste streams? Let's tanker it

发言人 1  00:02:54

out. Okay，I'll put it。

发言人 3  00:03:22

うんか。but was going to go in a tank.

发言人 2  00:03:29

嗯能。

发言人 1  00:03:30

呃。

发言人 2  00:03:32

对。

发言人 3  00:03:39

yeah yeah i guess it's more likely ibcs if it's only. 2000 LEAGUES.

发言人 2  00:03:48

But we just send it to STO three and put it out through the standard waste route. 嗯。It's mainly organic, but when we just work through

发言人 1  00:03:57

that. 谁。In terms of the action log, to confirm timelines for the feasibility study, so I've targeted the end of this week, so we're trying to aim for that still.

发言人 1  00:04:16

Um. Confirm access is required for all sizes of the column, so I think I've added that as a risk in the risk register at the moment.

发言人 1  00:04:29

So yeah, that's just held pump skid. We've had this discussion with the suppliers, so that information is being spent. And back, we just will put it on the model and feedback to you.

发言人 1  00:04:48

好，非常。Um, service void access around equipment. Uh, do any of the equipment's need to be drawn out of the shafts? So you have sent some information on that, and we've reviewed it.

发言人 1  00:05:01

So, but we just need to review it with Mike to make sure that we don't need to renudge any of the walls. But currently we think that.

发言人 1  00:05:09

You know, it's possible.

发言人 2  00:05:12

Peter's just sent some additional equipment on, so I'll put that into ACC later on today as well.

发言人 1  00:05:18

Equipment requirements, uh, is it just pumps or is it tanks?

发言人 2  00:05:25

Uh, no, the maintenance and access

发言人 1  00:05:27

requirements are maintained. 嗯，嗯。对，你就看看价格，看是不是。

发言人 4  00:05:43

如果再往下

发言人 1  00:05:44

掉一个，你就扔了，对不对？

发言人 4  00:05:49

行好嘞好嘞嗯

发言人 1  00:05:51

嗯嗯。好。Okay, um, spray dryers. I've just added that into the risk register. So I'm going to close that based on our discussion. And we just need

发言人 2  00:06:05

to make sure we... We are calling it a filter dryer, not a spray dryer.

发言人 1  00:06:09

Okay，a filter dry。I don't know what I put。Their spray dryer, I think I keep picking up this. Okay，I'll check my wording on that。

发言人 1  00:06:32

Okay, access to Dhum unit. This is the Dhum unit for the lyophilizer. There's just an action to confirm with the team locally.

发言人 2  00:06:47

Yeah, and that's some of the details that Peter's very kindly sent through, so that's from Sunday as well.

发言人 1  00:07:07

Okay, joke. So these items are closed. We happy we close these. It's a question from yourself, Rob. Please we discussed on Thursday equipment items to have a standalone control system.

发言人 1  00:07:21

So we've said they'll have their own PLCs. New equipment needs to be fed. Will any of the new equipment need to communicate with each other?

发言人 1  00:07:32

So we've just said the DAC does not need to speak to the lyophilizer, but it'll speak to the pumps kids. So I've closed that action. Will any new equipment need to be.

发言人 1  00:07:42

Communicated with the existing control system, so we've just said some signals back, so you did have some information back. Rob from Simon was that sufficient or not? Or have you had chance to review?

发言人 4  00:07:57

Yeah, I've had a look at that.  And it is useful.  I mean, I've got I've got a proper switch room layout now, which is which is good, and also the um I've got the IO count for the charms system.  And thanks Claire for forwarding that one. Uh,

发言人 4  00:08:09

It looks like there's plenty of spare IO to do what we need to do, so I don't have any concerns there.

发言人 1  00:08:17

I'm gonna close the action then, Rob. Yeah, is that okay? Yeah, because I think that was an RF you asked for drawings. Similarly, I think you've got some information back from Lewis last week. Is that sufficient? Are you happy about close action out or not?

发言人 4  00:08:36

Uh, yeah, close this particular one out. I mean, as I... As I dig through there, might be some other bits and bolts, but for the time being, I think I've got everything I've asked for so far.

发言人 1  00:08:45

Okay，good lyophilizer。discrepancy, so we've just closed that out. We've just assumed that is the larger electrical requirement.

发言人 1  00:08:56

And

发言人 2  00:08:56

so Peter's Peter's provided some more information on that as well, so there'll be a few bits come through to you later on.

发言人 1  00:09:05

Thank you. Okay, uh, is cleaning waste? It's just a question for yourself, Claire. Cleaning waste going to go to the new, uh, 2000-liter waste tank.

发言人 1  00:09:29

Yes, just had it as an action.

发言人 3  00:09:31

I think this is from the life laser, isn't it?

发言人 1  00:09:35

Yes, it is. Oh, the

发言人 2  00:09:36

edges would be okay.

发言人 3  00:09:41

After me, I didn't think it would go to the new waste tank, but

发言人 2  00:09:44

no, sorry. I thought you meant... I was assuming you meant the column, but no. 那一个。

发言人 1  00:09:50

no

发言人 3  00:09:50

okay so it's got got go somewhere but can it go into your one of your existing waste tanks.

发言人 2  00:10:00

check that. It's acris rice, isn't it? Acris.

发言人 3  00:10:07

They think us into what should be a simple system, so only if you've had a failure, but you need to account for how would we clean if you've had a failure

发言人 2  00:10:14

, yeah.

发言人 1  00:10:21

So we just confirm where they'll go into the existing one of the existing most banks. And then the CIP room with the hyper changes, you've sent that information, so we'll just try and complete that.

发言人 1  00:10:34

Just keep it open, actually. I'll just write a note to myself just to check the dimensions.

发言人 2  00:10:40

Filters at the moment, so yeah. 我们俩

发言人 1  00:10:46

嗯。Okay，good。Should we just go around the room to see if there's any discussion points that people have raised since they are generating the report?

发言人 1  00:11:04

Chris, have we got any issues that you want to raise or any further information you want from Claire?

发言人 3  00:11:10

No, it was just doing a bit of thinking over the weekend as you do. I mean, we are assuming that. None of the vent streams have to go to scrubber or anything like that, or if they do, then it's an existing.

发言人 3  00:11:25

Connection onto an existing vent. line which goes to the scrubber. I don't know if you had any other thoughts on that.

发言人 2  00:11:40

We hadn't thought about that at all. I was making an assumption it was going to go into the existing Ben headers.

发言人 3  00:11:46

不要去。YEAH, WE WILL DO THE SAME. 出してる？best system show the market yeah stated.

发言人 1  00:12:00

I'll add that to the risk register. is an assumption.

发言人 3  00:12:07

OTHER THAN THAT, UM, I DID START LOOKING AT THE WASTE ROOT FROM THE, UM, COLUMN. I DIDN'T LOOK TOO FAR BUT. 嗯。Guessing is there a way out of the.

发言人 3  00:12:26

Which way would we go? Would we go through into the service void to the. Jehovah's side that is east. AND THEN CAN WE GO STRAIGHT THEN THROUGH THE WALL AND UP OVER THE ROAD.

发言人 3  00:12:39

To where the waste tanks are, rather than have to go all the way back through the building and down and round as it were.

发言人 2  00:12:52

I quite imagine where you looking to go. Need to look at where the pipe brackets.

发言人 3  00:12:57

but which

发言人 2  00:12:58

pipe. Wait outside,

发言人 3  00:13:03

see if I still got it. No, I haven't.

发言人 2  00:13:15

Do you want to use existing pipe racks if you've got to go over the North Road?

发言人 3  00:13:21

yeah.

发言人 2  00:13:22

I don't know where you're envisaging the waste tank being situated,

发言人 3  00:13:28

so this is obviously pilot plant. So you see one modules up this end isn't it already? Yeah, yeah. And then you got the service module at the end.

发言人 3  00:13:38

I just noticed there's some pipes here. There's some pipes. So I think a lot of your existing route is across the pipe rack here, and then down, and your waste tanks are all in this region. We were thinking of putting a new one.

发言人 3  00:13:51

Probably somewhere here, so it's a question whether we have to go back all the way through the building, then down and around, or whether there is a route where we can just come into this service void and go through.

发言人 2  00:14:03

Can you just put an action for me to confirm that we can use that and there isn't some pre-segregation that I'm not aware of?

发言人 3  00:14:10

いや、It's obviously quite a bit further, but.

发言人 2  00:14:18

That is, yeah.

发言人 3  00:14:21

But if that's what you have to do, that's what you have to do.

发言人 2  00:14:23

Logistically, it would make sense if the less is a reason why we can't use that rack. But then what I need to go and check, yeah, I need to go and check some deals, what's exactly is on that rack.

发言人 3  00:14:38

yeah it's probably cause that's your nitrogen tank cause it's probably nitrogen and. Maybe your hair goes that way.

发言人 2  00:14:45

Yes.

发言人 3  00:14:47

キドーク。YOU GOT THAT ONE QUEEN.

发言人 1  00:14:52

YEAH, I'M JUST ASKING YOU THAT.

发言人 3  00:14:55

Oh, by the way, have Nick the share if you are still sharing your action list.

发言人 1  00:14:59

It's fine, no I... I understand. 哎，对。Um, I'll just put an actual beef that... Sorry. Uh, anything from you Rob that you wanted to talk about?

发言人 1  00:15:28

And then any items you want to raise.

发言人 4  00:15:34

No, nothing in particular is reasonably straightforward from an electrical point of view. I'm making a assumption that we're going to put into new containment for the time being, for the new items, even if there is containment up in the void.

发言人 4  00:15:49

Potentially got from some free space in it, but um, we don't have a sufficient level of detail to determine what's what's there and whether there's space, so we'll just assume that we need new containment for the time being, um.

发言人 4  00:16:01

And then from a controls point of view, I'll allow for some new local IS marshalling boxes for the new items of equipment, so that we're not interfering with any of the existing.

发言人 4  00:16:16

Uh, boxes because of some changes in legislation we would have to do an assessment of their suitability, the old boxes. So we'll, we'll put some new ones in so that we don't need to change any of those existing.

发言人 4  00:16:31

UM BY JBS.

发言人 1  00:16:36

Okay, if they're in the cost, then that's great, and then they can be removed later. I guess if you decide that you do want to utilize what's there.

发言人 4  00:16:47

Yeah, essentially, I mean in the in the in the A in the A text race, we have to use EXE marshalling boxes for anything that's got more than one IS circuit in it now.

发言人 4  00:17:00

Whereas when the building was put together, I don't think that was a requirement. So as soon as we start changing circuits in there, then we end up having to do a lot more work to assess whether they're suitable or not.

发言人 4  00:17:11

So I'm just kind of keeping it separate for the zombie.

发言人 1  00:17:16

对下ay thanks well. Claire Scott, anything on your end that you want to discuss?

发言人 2  00:17:26

这能谁？

发言人 1  00:17:30

一天。The Chinese team, Peter, did you want to discuss any items?

发言人 3  00:17:37

呃郭郭郭工您看咱们还有什么这个啊需要跟他们讨论的关于前面那几项。

发言人 1  00:17:50

啊，我这里

发言人 3  00:17:50

没有。yeah，uh we are good yeah nothing yeah thanks.

发言人 1  00:17:57

Okay, good. Um, I've just got one item clear just to talk about, um, just a cost estimate for the feed and for the detailed design.

发言人 1  00:18:05

Um, did have a quick discussion just internally around this. And perhaps if you're okay with it, we put the feeds and the detailed design together or the hours might merge from one to the other. Our concern is that we might not get.

发言人 1  00:18:24

Enough information back from the packages at the feed stage to be able to do a really good feed study. And it may be that once you place the order, then that's when some of the information will be obtained.

发言人 1  00:18:39

And as a result of that, we do some of the activities we normally do in feed within the detailed design. So we can estimate separate hours for them, but it may be that we might not use the hours.

发言人 1  00:18:51

All the outsourcing, but they'll roll on to the detailed design. Is that

发言人 2  00:18:55

be acceptable? Yeah, yeah, that would be.

发言人 1  00:18:59

So we will estimate, they try and estimate the hours separately, but there is concern just a risk from our side that you might hold us to it and then say, well, we moved on to detailed design and you haven't used all your hours for feed, but.

发言人 1  00:19:12

This is all you've got for the detailed design.

发言人 2  00:19:16

That was okay.

发言人 1  00:19:18

Okay，good。

发言人 3  00:19:20

对。

发言人 1  00:19:22

And obviously we'd one of the items we've said in the risk register is around freezing of the design as soon as possible, as well because that allows us to make sure that we the cost estimate I'm assuming you still want a cost estimate at feed.

发言人 1  00:19:35

Do you have the plus thirty? So we're on the same page. Is it yet? So you're after a plus thirty percent at feed and a plus ten percent at detailed design. Are you? Is that the stage gates you normally go through?

发言人 2  00:19:49

There are different stage gates in China, but yes, that's what we would expect in the UK.

发言人 1  00:19:54

Okay, okay, that's what we normally work to, but we're obviously can work to what whichever numbers that you want to. It's just that it determines the amount of detail we need to go.

发言人 1  00:20:03

It depends where

发言人 2  00:20:04

the work is, doesn't it? If you... if we said you wanted plus or minus 10% of feed, we're essentially doing detailed design anyway

发言人 1  00:20:10

. Yeah. Yeah, yeah, yeah. It agreed. It's just, uh, just want to be clear so that, uh, we're not talking about different things at that time.

发言人 2  00:20:18

That's not what it.

发言人 1  00:20:20

excellent um i don't really have anything from my side did you want me to jump onto the risk register claire to review the risk register

发言人 2  00:20:27

or yes please

发言人 1  00:20:29

yeah okay

发言人 2  00:20:30

let's have a list that just have a list have a quick look at it and then we can see if there's anything else.

发言人 1  00:20:34

That we think. Let me just open it. It's on the shared area there as well, and if you wanted to have a look at it. Okay，the first item is around modifications to existing facilities not in beneficial use by quarter three，twenty twenty seven.

发言人 1  00:21:06

So in order to mitigate that, we're saying order the long lead items as soon as possible, prioritize finalization of the design of the long lead items and feed and place the orders.

发言人 1  00:21:18

在。I don't know whether we'd be happy and feed with the uncertainty, but I guess we can when we get there.

发言人 2  00:21:29

And then that and I think we can then go back and talk to the organisation so that they understand to meet the timelines. This is where, yeah.

发言人 2  00:21:37

WHERE THE RISK LIES AND WHERE WE NEED TO SPEND MONEY, SO. It's useful to tab it on here.

发言人 1  00:21:44

Okay. Long lead time items extend the program excessively. So yeah, work with the suppliers to understand the schedule and expedite, manage equipment deliveries to ensure there's no program slippage.

发言人 1  00:21:59

So we have had it in the past where we've purchased items from the Far East and they've said it's a 10-week delivery and it's not come for.

发言人 1  00:22:10

Almost half a year, so sometimes a little longer. So we've got one at the moment that is still in production after a year. So wow!

发言人 1  00:22:20

Okay, yeah,

发言人 3  00:22:21

to be fair that's India, not China.

发言人 1  00:22:24

India, India... Not yeah, the Chinese equipment that we bought actually came a lot faster. 你把u're right, Chris. UM, A MEN'S CURRENT ENVIRONMENTAL MENTAL PERMIT, UM, SORRY, RISK THAT THE AMENDMENT TO THE CURRENT ENVIRONMENTAL MENTAL PERMIT IS NOT AGREED SO EARLY APPLICATION ENGAGEMENT WITH THE EA EA FOR.

发言人 1  00:22:45

buying.

发言人 2  00:22:46

嗯。

发言人 1  00:22:48

HPLC or lyophilizer cannot make materials to the required quality, so we've basically said experience in house with the AssemChem Chinese team, similar facilities being operated in China.

发言人 1  00:23:01

This item is not deemed a risk for this project. What do you think about that comment? Is it a risk or not? I think it probably is.

发言人 1  00:23:10

Because you use, you're probably doing. different materials risk is, yeah, we're doing a different application. Well, same application with a different installation.

发言人 1  00:23:18

But I think the comments are right, and then the rating ultimately is probably correct. It comes down to low risk, yeah. Okay，I'll be gonna remove this last comment again。

发言人 1  00:23:32

equipment costs from China seem low and have the potential to escalate, so and mitigation thorough discussions with supplier to ensure that the equipment is specified to the appropriate.

发言人 1  00:23:44

Appropriate process requirements, equipment to be CE marked, so should be suitable for supply into Europe. Ensure that any equipment conforms to UK standards and or machine regulations, thorough review of documentation to understand scope supply.

发言人 1  00:24:03

Um, and then Asim Ken Chinese team have a historical experience with preferred suppliers. Is that true? Is that comment true of the suppliers that you're using at the moment, Peter?

发言人 1  00:24:14

That you've suggested, have you actually used them before? うん。My understanding is yes, is the answer to that question. we've seen a hand bomb, yeah we've seen the equipment installed, okay?

发言人 1  00:24:29

And I'm assuming we've got toflon equipment as well. I believe we have used them before. Okay, so the risk is low if you've used them.

发言人 1  00:24:38

You've got good experience with them. But I agree with you, the price seems very low. But that's probably why you go in that route as well.

发言人 1  00:24:49

Is about is it about three or four times more expensive purchasing it in the UK? Yeah, and that sort of concerns me slightly. We haven't... We may need to add the main elements that we haven't got fully spec.

发言人 1  00:25:01

BUT YEAH. I think it's still low at the moment. Shall I change that probability to two then until we work through a bit more of the design?

发言人 1  00:25:14

yes, i think that's fair. 嗯。I think certainly with the CE marking now we've pushed them about kind of a smaller unit, smaller footprint unit, whether that's actually been built CE marked. Yeah, that's a good call.

发言人 1  00:25:29

But they also wrote in that note that they've built a smaller unit for another customer, and that's I don't know where the customer sits, whether it's in China or in the UK, but essentially said.

发言人 1  00:25:44

OKAY. Okay, we'll leave it at that. And then we can leave it at that. Yeah, I think that's fair. Yeah, we can always review later as we progress through the project because hopefully all of these risks will have mitigated in some way or other.

发言人 1  00:25:59

Construction equipment supplied from China is of poor quality, so due diligence on the manufacturer to ensure that the base quality of equipment is good. Fat inspection visits to be completed.

发言人 1  00:26:13

And then I've also said Asim Kem Chinese team have historical experience with the preferred suppliers, so we should be able to mitigate that.

发言人 1  00:26:23

Existing utilities are not sufficient to operate the facility. Assem came to have discussions with equipment supplier to understand the utility requirements, which you have done. Utility schedule to be generated to summarize those.

发言人 1  00:26:38

Discussion and feed phase to determine acceptable diversity, so we might be able to. Just tweak it a little bit more during feed.

发言人 1  00:26:49

There's no clear schedule or end date, high level timeline provided by Athens and Hem. So you've said that you wanted quarter three 2027 RB plant to provide high level.

发言人 1  00:27:01

Overall project program during the feasibility study, and this will be further developed during the feed stage. Yeah, uh, s- stuffing for operational readiness has not been costed or allowed for, so training requirements to be developed during the feed stage to enable these gaps to be addressed.

发言人 1  00:27:23

So, because have you run this operation before at Sandridge? But yeah, I guess you can get that information from the Chinese team as well.

发言人 1  00:27:33

对。Yes. Maintenance requirements for the HPLC lyophilizer are not clearly defined, so we're working with the suppliers at the moment to understand requirements, and we'll definitely have further discussions during the feed stage.

发言人 1  00:27:49

to minimize that. Funding strategy for yourself, client. I've just written here, client has a clear funding strategy. I've just said as in Ken to score, is that true? Are these scores essentially?

发言人 1  00:28:06

Do you have a clear funding strategy? Is it likely to go ahead? Depends by what you mean strategy. I would have said we do not have, we do not have definitive funds allocated at the moment.

发言人 1  00:28:21

Part of the output from the feasibility study at the moment is to agree funding. Okay。So unmitigated, I've said three and four.

发言人 1  00:28:31

So three is in terms of probability may occur if no effective action is taken and impact is quite high because. I guess it's time or.

发言人 1  00:28:44

you may not be able to deliver it in a certain time. I can delete it as a risk if you want. Oh, yeah, it doesn't have to be on the risk to the risk of the program.

发言人 1  00:28:54

It's the risk of meeting the timelines. I would leave it at three and four currently, yeah. and then mitigated if you had a shall i leave it as three and four for the time being until i guess the feasibility study is completed and then you can.

发言人 1  00:29:11

speak internally about it, yeah, yeah, uh, so capex costs are higher than expected, so I've said value engineering exercise to rationalize equipment items and scope.

发言人 1  00:29:24

If we need to, this is in feed fast track development of costs for piping and equipment installation to achieve a better accuracy.

发言人 1  00:29:34

Throughout throughout the project life cycle, challenge process requirements to minimize capex costs where possible. I actually think that probably your capex is probably going to come out quite low.

发言人 1  00:29:47

啊嗯。I think the reality is, buying equipment from China you will find it much lower, so. Shall I leave this unscored for the time being, and then we can revisit?

发言人 1  00:29:59

Once we've got the estimates out. 嗯。Remediation actions post fat on the equipment extend delivery times, so I've said litigation to be confirmed on that.

发言人 1  00:30:16

Because that's one of the items that we had an issue with with the equipment that we have procured recently that when we've done the factory acceptance test, we've then had to ask them to do.

发言人 1  00:30:29

Remediation on the work. From your point of view, the cost of the project outweighs its financial benefits. So business case to be fleshed out throughout at each milestone to track financial benefit.

发言人 1  00:30:45

I've left it unscored because these are kind of sitting in your court, yeah? I would leave that unscored, yeah. 嗯。There will be scope creep in the project requirements, including the addition of new equipment items and material handling.

发言人 1  00:31:00

So I've basically said requirements through frozen during the first stages of feed. And we'll continue to review the scope throughout the project, so yeah.

发言人 1  00:31:11

We don't want it to grow, if possible. 嗯。So operation of spray dryer, I'm now thinking filter dryer. I don't know why I have it in my head.

发言人 1  00:31:28

FILTER DRYERS ARE REQUIRED DURING DEMOLITION AND INSTALLATION OF LYOPHILIZER, SO I'VE JUST WRITTEN IN WHAT WE SAID LAST WEEK AROUND THE FACT THAT WE HAVE SHORT AH VISIT TERM VISIBILITY OF OPERATIONAL DEMANDS.

发言人 1  00:31:40

So I've just left it scored quite high for the time being. Um, poor maintenance access around the equipment, so feasibility to include access for maintenance of equipment.

发言人 1  00:31:53

So I think we're mitigating it, but we'll get more information during the feed, obviously. So another similar one, there is poor access for maintenance on existing equipment, so we will keep reviewing that.

发言人 1  00:32:09

Access routes compliant for the fire reg, so we'll review the layout during the feasibility study and amend as necessary. So currently there's no concerns from Mike's point of view on this.

发言人 1  00:32:23

But as we keep changing or tweaking the equipment, we will obviously continue to review. Filter drying lyophilizer cannot be operated at the same time as it contravenes quality and regulatory control.

发言人 1  00:32:39

So we've put that as a risk, but it's low at the moment based on. The discussions you've already had with the quality team. The introduction of new equipment into the building cannot be achieved without modification to existing access routes, so we've said early assessment of this is to bring the equipment in.

发言人 1  00:33:01

So Mike said that it's possible, so he's happy with it. So he's done an early assessment and he said that that's not too much of an issue.

发言人 1  00:33:12

personnel in and out entry system airlock required so that can be accommodated low risk by access and egos resourc so. Surveys completed and initial studies think we believe are compliant.

发言人 1  00:33:31

Temperature control within the rooms cannot be controlled adequately asso. probably unable to confirm this as we don't really have any information about how much heat the equipment, the new equipment is going to dissipate.

发言人 1  00:33:51

And we'll work on that as the project progresses. So there is an option which will cost money, obviously, to put a separate cooling package in.

发言人 1  00:34:02

On that, but we're obviously space constrained as well. So it scored accordingly on that. Um, ergonomics around the deck, and so we just kept that as a risk.

发言人 1  00:34:19

At the moment, uh, we just... there's, there's a couple of items around the manual handling of the piston ends and the actual piston itself, so I've just put that as a discussion item in the wristregister.

发言人 1  00:34:34

Similarly, CE certification and equipment. So we for the feasibility stage, we've assumed no gaps for the time being. Because it's C marked and we're assuming that it's suitable to come into the UK.

发言人 1  00:34:48

嗯。No suitable time points for the HTF without draining down the system fully. So we've just said include costs of replacement HRTF is included in the CapEx.

发言人 1  00:35:05

Also we need to think about the impact on other equipment items that use HRTF. That there may be some downtime associated with those equipment items.

发言人 1  00:35:16

And that's going to be a key task, I think, in the feed studies, understanding what that downtime is going to look like, so that we can then schedule that in.

发言人 1  00:35:25

appropriately. Okay, I wrote this, but I don't know. We probably need to discuss a mechanism of drying post CIP activities. Do we need to dry the equipment after we've cleaned it?

发言人 1  00:35:43

I don't know if it's a question that's been asked at all. We have asset actually uses water wet isn't it so. I DON'T KNOW. I don't know enough about the equipment to be able to answer that question.

发言人 1  00:36:01

I'll leave it on then, and then we can score. Okay，purified CIP water doesn't have sufficient capacity。I've said to confirm if this is a risk。Chris，did you think this was a risk at all？

发言人 1  00:36:30

um i mean it's similar to all the other utilities it's it's always a risk until you've um. closed it out. I MEAN WE HAVEN'T, WE HAVEN'T GOT A AH SIGHT OF.

发言人 1  00:36:44

What the usage included any diversity is of the existing system. And so we've not looked at what the new system impact will be. It probably is low, but until we've had a proper closer look at that, you can't say you've closed it out.

发言人 1  00:37:06

Okay, I'll say we will leave it as a risk, but we'll store once we have further information, I guess. Room balancing cannot easily be achieved in the isolated area, so for the feasibility study we assume that the isolator is running all the time.

发言人 1  00:37:34

And then I guess, uh, yeah, yeah, this is just for balancing it, I guess. And then the wall is not needed between the lyophilizer and the vacuum pump.

发言人 1  00:37:46

So for the feasibility study, we've assumed that we do need it. 在。Those are the risks that have been raised so far. I think I had a risk today, which I will add on.

发言人 1  00:37:58

Are there any other risks that have not been kind of considered? It's obviously a live document, so we'll continue adding to it as we talk through the electrical replacement.

发言人 1  00:38:10

that we discussed earlier. Is there anything else on the electrical or the demolition that we need to capture? 那就为什对。looking from a demolition perspective in terms of.

发言人 1  00:38:32

electrical. I think was any particular, yeah, no, okay. Oh, I sorry, was that question for me? I had a visitor in the office, and I missed it.

发言人 1  00:38:43

Yeah, was there anything from electrical perspective that needs to be on the risk register? Um, you mentioned about having to replace something earlier.

发言人 1  00:38:53

Yeah, I think, I think for the purposes of the feasibility study, and I think for also for the scope of this particular project.

发言人 1  00:39:01

I think it's best to keep the new equipment controls separate from the existing, at least in the field. It can go back to the main cabinet.

发言人 1  00:39:13

But then I think we should leave the IJBS that you have in the field alone. Okay，because of uh，I mean I would recommend that that um Asin can take a look into the issue long term，but it's not for the scope of this project I would say。

发言人 1  00:39:29

对。Thank you。Okay, let me know if you want some more details as to the requirements, and I can share that. Do you need anything else on that?

发言人 1  00:39:49

no, i think that's good. thank you. Okay。Uh, any other bits anyone wants to raise? from the project. No thanks. Okay, good. Um, so we're still targeting to next week Claire for the report out, um, from all of the disciplines.

发言人 1  00:40:16

Um, I'll let you know whether we get anything back from the supplier. FOR THE COSTS COLEMAN AND JAMES. If you do think we need to move the meeting, the earlier you can let me know the better, because then it will be easier to try and reschedule it.

发言人 1  00:40:33

Okay, okay, good, good. Let me try and get hold of Mike, see what he's got to with them. Brilliant, okay? If no one's got anything else, and thanks very much for your time, and we'll speak soon.

发言人 1  00:40:47

Thank you. Thank you. Bye.