## 2.0.1.Elemental Summary
G-128 Alterations
Concept Cost Plan
2.0 SUMMARY
2.0.1 Elemental Cost Plan Summary - Level 1 |  |  |  |  | Previously
|  | GIFA | 215 | m2 | 215 | m2
Ref | Element |  | Total £ | £/m2 | Total £ | £/m2 | Comments
0 | Facilitating Works |  | 65567 | 304.9628 | 0 | 0
2 | Superstructure |  | 68690 | 319.4884 | 0 | 0
3 | Finishes |  | 58898 | 273.9442 | 0 | 0
4 | Fittings, Furnishings and Equipment |  | 765000 | 3558.1395 | 0 | 0
5 | Services |  | 537573.75 | 2500.343 | 0 | 0
| Facilitating and Building Works |  | 1495728.75 | 6956.8779 | 0 | 0
9 | Preliminaries (incl. Contractor's design) |  | 362500 | 1686.0465 | 0 | 0
10 | Overheads and Profit | 5% | 92911.4375 | 432.1462 | 0 | 0 | % adjustment
| Total Building Works Estimate |  | 1951140.1875 | 9075.0706 | 0 | 0
11 | Professional Services |  | 141800 | 659.5349 | 0 | 0
| SUB-TOTAL |  | 2092940.1875 | 9734.6055 | 0 | 0
12 | Equipment (supplied by the Client) |  | 1975045 | 9186.2558 | 0 | 0
| SUB-TOTAL |  | 4067985.1875 | 18920.8613 | 0 | 0
13.1 | Design Development Risk (Refer to Risk Register) |  | 397875 | 1850.5814 | 0 | 0
13.2 | Construction Risk |  | incl above |  | 0 | 0
| Risk Allowance Estimate |  | 397875 | 1850.5814 | 0 | 0
| COST LIMIT (excluding inflation) |  | 4465860.1875 | 20771.4427 | 0 | 0
14 | Inflation | 2.154% | 96183.8811 | 447.3669 | 0 | 0 | % adjustment
| COST LIMIT (including inflation) |  | 4562044.0686 | 21218.8096 | 0 | 0
15 | VAT | Excluded | 0 | 0 | 0 | 0
| Total |  | 4562044.0686 | 21218.8096 | 0 | 0
| Construction |  | 1422940.767
| Equipment |  | 2732659.0317
| Risk |  | 406444.27
4562044.0686
| Construction Estimate Accuracy | 20% | 1710000
|  | -10% | 1280000
| Equipment Estimate Accuracy | 20% | 3280000
|  | -10% | 2460000
| Estimate Accuracy | Upper Limit | 4990000
|  | Lower Limit | 3740000
[5 empty] | 4562044.0686 | #DIV/0!

## 2.0.2.Elemental Summary
|  |  |  | G-128 Alterations |  |  | Lab | 181.8
|  |  |  | Concept Cost Plan |  |  | Write up Up | 33.3
[7 empty] | GIFA | 215.1
2.0 SUMMARY
2.0.2 Elemental Cost Plan Summary - Level 2
|  | GIFA | 215 | m2
Ref | Element |  | Total £ | £/m2
0.1 | Strip Out, Alterations and Demolition (partitions and the like) |  | 46967 | 218.4512
0.2 | Strip Out (services) |  | 18600 | 86.5116
0 | Facilitating Works |  | 65567 | 304.9628
2.7 | Internal Walls and Partitions |  | 42440 | 197.3953
2.8 | Internal doors |  | 26250 | 122.093
2 | Superstructure |  | 68690 | 319.4884
3.1 | Wall Finishes |  | 9810 | 45.6279
3.2 | Floor Finishes |  | 23631 | 109.9116
3.3 | Ceiling Finishes |  | 25457 | 118.4047
3 | Finishes |  | 58898 | 273.9442
4.1 | General fittings, furnishings and equipment |  | 765000 | 3558.1395
4 | Fittings, Furnishings and Equipment |  | 765000 | 3558.1395
5.3 | Disposal installations |  | 3000 | 13.9535
5.4 | Water installations |  | 38600 | 179.5349
5.6 | Heating, Ventilation and Air Conditioning |  | 217920 | 1013.5814
5.8 | Electrical installations |  | 107380 | 499.4419
5.11 | Fire and lightning protection |  | 30030 | 139.6744
5.12 | Communication, security and control systems |  | 51345 | 238.814
5.13 | Special installations |  | 63700 | 296.2791
5.14 | Builder's Work in Connection with Services |  | 25598.75 | 119.064
5 | Services |  | 537573.75 | 2500.343
| Facilitating and Building Works |  | 1495728.75 | 6956.8779
9.1 | Temporary Works |  | 10500 | 48.8372
9.2 | Site Welfare and Accommodation |  | 21000 | 97.6744
9.3 | Design and Construction Management |  | 331000 | 1539.5349 |  | 22.13%
9 | Preliminaries (incl. Contractor's design) |  | 362500 | 1686.0465
10 | Overheads and Profit | 5% | 92911.4375 | 432.1462
| Total Building Works Estimate |  | 1951140.1875 | 9075.0706
11 | Professional Services |  | 141800 | 659.5349 |  | 7.268%
| SUB-TOTAL |  | 2092940.1875 | 9734.6055
12 | Equipment (supplied and installed by the Client) |  | 1975045 | 9186.2558
| SUB-TOTAL |  | 4067985.1875 | 18920.8613
13.1 | Design Development Risk |  | 397875 | 1850.5814
13.2 | Construction Risk |  | incl above |  | 397875 | 9.781%
| Risk Allowance Estimate |  | 397875 | 1850.5814
| COST LIMIT (excluding inflation) |  | 4465860.1875 | 20771.4427
14 | Inflation | 2.154% | 96183.8811 | 447.3669
| COST LIMIT (including inflation) |  | 4562044.0686 | 21218.8096
15 | VAT | Excluded | 0 | 0
| Total |  | 4562044.0686 | 21218.8096

## 2.0.2.0_Facilitating Works
G-128 Alterations
Concept Cost Plan
2.0.2.0 FACILITATING WORKS
Item | Description | Qty | Unit | Rate | Total
1 | Strip Out, Alterations and Demolition (partitions and the like)
| Disconnect and remove antistatic plate adjacent to G128 entrance and set aside for possible re-use by Landlord | 1 | item | 350 | 350
| General clearance of furniture and laboratory equipment | 1 | item | 7000 | 7000
| Remove floor coverings, skirtings etc and dispose | 180 | m2 | 24 | 4320
| Remove suspended ceiling and dispose | 27 | m2 | 11 | 297
| Carefully remove existing door between G128 and G128D and set aside for re-use if required | 1 | item | 350 | 350
| Carefully take down and remove existing blockwork wall between G128 and G128D and dispose | 1 | item | 4500 | 4500
| Form openings through reinforced concrete wall for pass through hatch | 2 | nr | 4500 | 9000
| Form openings through reinforced concrete wall for doorway | 2 | nr | 9000 | 18000
| Carefully remove existing doors between G128B-G128C and G128B-G128A, and set aside in store for re-use by Landlord if required | 2 | nr | 1200 | 2400
| Take out glazed screen and set aside for reuse by Landlord - Proposed doorway to write up area | 1 | item | 750 | 750
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 46967
2 | Strip Out (services)
| Isolate and remove gas pipework / services | 1 | item | 6000 | 6000
| Disconnect and remove ventilation ductwork | 1 | item | 4000 | 4000
| Disconnect and remove electrical installation including light fittings and containment where required | 1 | item | 3000 | 3000
| Isolate from main FA panel, disconnect and remove smoke detectors | 1 | item | 800 | 800
| Isolate, disconnect and remove Crowcon system | 1 | item | 1600 | 1600
| Isolate, disconnect and remove sink and cupboard from Room 2 and store for re-use / possible relocation to other side of wall later | 1 | item | 600 | 600
| Isolate, disconnect and remove flow and return pipework, cap off above ceiling level | 1 | item | 600 | 600
| Isolate, disconnect and remove services from store cupboards | 1 | item | 2000 | 2000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 18600

## 2.0.2.2_Superstructure
G-128 Alterations
Concept Cost Plan
2.0.2.2 SUPERSTRUCTURE
Item | Description | Qty | Unit | Rate | Total
2.7 | Internal Walls and Partitions
| Wall lining; double skin tape and joint ready for decoration | 475 | m2 | 72 | 34200
| Infill opening between Rm2 and Rm3 where door removed | 3 | m2 | 250 | 750
| Box in hydrogen pipework in Rm3 (opposite door D3 - Changing room door); extra over item above for wall lining | 1 | item | 850 | 850
| New partitions; 70mm stud, 2 layers 12.5mm soundblock each side, 25mm APR jointed ready for decoration. | 40 | m2 | 166 | 6640
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 42440
2.8 | Internal Doors
| Doorsets; single leaf; semi flush hygenic doors | 5 | nr | 3250 | 16250
| Doorsets; leaf and half; semi flush hygenic doors | 1 | nr | 4800 | 4800
| Doorsets; single leaf; timber to write up space | 2 | nr | 1800 | 3600
| Allow for refurbishing existing doors | 4 | nr | 400 | 1600
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 26250

## 2.0.2.3_Finishes
G-128 Alterations
Concept Cost Plan
2.0.2.3 FINISHES
Item | Description | Qty | Unit | Rate | Total
3.1 | Wall Finishes
| Decorate walls to lab | 475 | m2 | 18 | 8550
| Decorate walls to write up area | 70 | m2 | 18 | 1260
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 9810
3.2 | Floor Finishes
| New sheet vinyl floor to lab | 173 | m2 | 111 | 19203
| Allow for coved skirting | 136 | m | 18 | 2448
| Allow for new carpet in proposed write up area | 33 | m2 | 60 | 1980
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 23631
3.3 | Ceiling Finishes
| New metal suspended ceiling to lab | 173 | m2 | 133 | 23009
| Allow for perimeter detail (tbc) | 136 | m | 18 | 2448
| Assumed ceiling to write up area retained and no works required |  |  | 0 | 0
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 25457

## 2.0.2.4_FF&E
G-128 Alterations
Concept Cost Plan
2.0.2.4 FITTINGS, FURNISHINGS AND EQUIPMENT
Item | Description | Qty | Unit | Rate | Total
Furniture
| General allowance for furniture including lockers; step over bench; mobile benches & BIBO bins | 1 | item | 20000 | 20000
| Allow for furniture for write up space | 1 | item | 5000 | 5000
Equipment
| Isolators; provisional allowance | 4 | nr | 150000 | 600000
| Isolators; provisional allowance | 1 | nr | 100000 | 100000
| Fume Hoods; assumed existing Fume Hoods are serviceable; provisional allowance made for servicing and repairs if required | 1 | item | 20000 | 20000
| Allow for SF6 Testing | 1 | item | 20000 | 20000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 765000

## 2.0.2.5_Services
G-128 Alterations
Concept Cost Plan
2.0.2.5 SERVICES
Item | Description | Qty | Unit | Rate | Total
Disposal installations
| Allowance for drainage connections (sinks & shower) | 1 | item | 3000 | 3000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 3000
Water installations
| Allowance for H&CWS installation (sink and mist shower) | 1 | item | 3000 | 3000
| Take from store and reinstall sink and under cupboard unit | 1 | item | 600 | 600
| Provisional allowance for mist shower | 1 | item | 35000 | 35000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 38600
Heating, Ventilation and Air Conditioning
| Allow for AHU maintenance / bring the system back into use | 1 | item | 20000 | 20000
| Allow for complete ductwork installation to laboratory, including supply air diffusers and extract grilles | 182 | m2 | 560 | 101920
| Allow for HEPA filters to extract ductwork (Bag in/bag out) | 1 | item | 42000 | 42000
| BMS upgrade; provisional allowance for disconnecting existing BMS controls, provision of new control panel, interfaces with system and commissioning | 1 | item | 50000 | 50000
| Allow for balancing of system | 1 | item | 4000 | 4000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 217920
Electrical installations
| Small power installation to lab | 182 | m2 | 420 | 76440
| Lighting installation to lab | 182 | m2 | 170 | 30940
| Allow for equipment connections |  |  |  | incl above
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 107380
Fire and lightning protection
| Allow for installation of sprinkler system to lab | 182 | m2 | 165 | 30030
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 30030
Communication, security and control systems
| Access Control to lab entrance door and write up space access | 3 | nr | 3000 | 9000
| Structured cabling installation to lab and write up areas | 215 | m2 | 45 | 9675
| CCTV to lab and write up areas | 215 | m2 | 80 | 17200
| Fire alarm system to lab | 182 | m2 | 85 | 15470
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 51345
Special installations
| Laboratory gas pipework installation | 182 | m2 | 350 | 63700
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 63700
Builder's Work in Connection with Services
| Allow for forming holes; fire stopping & access hatches | 5% |  | 511975 | 25598.75
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 25598.75

## 2.0.2.9 Prelims and Staff
G-128 Alterations
Concept Cost Plan
2.0.2.9 CONTRACTOR'S PRELIMINARIES AND STAFF
Item | Description | Qty | Unit | Rate | Total
Temporary Works
| Allow for temporary protection to retained equipment and common areas for the duration of the works | 1 | item | 10000 | 10000
| Allow for temporary lighting | 1 | item | 500 | 500
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 10500
Site Welfare and Accommodation
| Welfare and accommodation provided during the construction phase | 21 | wks | 1000 | 21000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 21000
Design and Construction Management
| Surveys | 1 | item | 20000 | 20000
| Concept and Co-Ordinated Design [RIBA 2/3] - Contractor's Design including PM and Commercial input | 1 | item | 80000 | 80000
| Detailed Design [RIBA 4] - Contractor's Design including PM and Commercial input | 1 | item | 44000 | 44000
Construction Stage Resourcing [RIBA 5]
| People and Expenses | 22 | wks | 8500 | 187000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 331000

## 2.0.2.11 Professional Services
G-128 Alterations
Concept Cost Plan
2.0.2.11 PROFESSIONAL SERVICES
Item | Description | Qty | Unit | Rate | Total
Project Management
| Pre Contract (av 1 day per week) | 33 | wks | 600 | 19800
| Post Contract (av 1.5 days per week) | 22 | wks | 900 | 19800
| Defects Period | 10 | Days | 600 | 6000
Design Support
| Pre Contract | 1 | item | 10000 | 10000
Commercial Support & Contract Administration
| Pre Contract | 1 | item | 35000 | 35000
| Post Contract | 22 | wks | 2100 | 46200
| Contract close & Final Certificate | 1 | item | 5000 | 5000
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 141800

## 2.0.2.12 Client Equipment
G-128 Alterations
Concept Cost Plan
2.0.2.12 EQUIPMENT (SUPPLIED AND INSTALLED BY THE CLIENT)
Item | Description | Qty | Unit | Rate | Total
Equipment
| Equipment; refer to Equipment list "Equipment List Costs for scoping 5 Aug" | 1 | item | 1975045 | 1975045
|  |  |  | To Elemental Cost Plan Summary - Level 2 | 1975045