## Slide 1
Asymchem UK — B902 PDF Extension
Investment & Programme Briefing for Group COO/CFO Feasibility Study (RIBA Stage 1) | Discovery Park, Sandwich | May 2026
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)

## Slide 2
Executive Summary
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Conclusion: Extension is feasible subject to planning approval (Scitech executive summary).
Investment (OOM, May 2026 base): £78,108,089 total project cost; base construction £47,591,969.
Scale: 3,099 m² GIFA (~600 m² footprint, 4 floors + plant mezzanine).
Schedule: Feasibility complete; Concept design planned from Jul 2026; construction Aug 2028–Nov 2029; project complete May 2030 per programme.
Decision: Approve progression to RIBA Stage 2 and confirm baseline Option 1 (hydrogenation building removal).

## Slide 3
Project Overview
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Asset: Existing B902 PDF pilot plant — east-side extension for reactor scale-up & new suites.
Scope: 10 reactors (R25–R34), 2,500 L hydrogenation reactor (R35), 3 filter dryers, handling/milling/continuous areas, HVAC & utilities.
Designer: Scitech-EKIUM under contract to Asymchem (Project 300291).
Baseline design: Option 1 — remove/relocate existing hydrogenation building; highest score in option appraisal matrix.

## Slide 4
Current Progress
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
RIBA Stage 1 Feasibility Report & appendices issued (Rev A1, 22 May 2026).
Feasibility walkthrough with UK team: 27 May 2026.
Pre-planning pack in preparation for local authority engagement.
Outstanding: B902 operating data gaps; final confirmation of procurement split; Stage 2 contract / fee proposal (not in published FS pack).

## Slide 5
Investment Structure (OOM)
Feasibility-stage order-of-magnitude — not final Capex
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Chart: 
| Published OOM total
Direct works | 41968226
Preliminaries & OH&P | 5623743
Other project costs | 4062357
Risk & contingency | 26453763
Total OOM | £78,108,089
Base construction cost | £47,591,969
→ Direct works subtotal | £41,968,226
Other project costs | £4,062,357
Risk & contingency (incl. register) | £26,453,763
Unit cost (GIFA) | £25,204/m²
GIFA (feasibility) | 3,099 m²
Excludes: inflation/FX/tax; client PM & operational costs. Cost plan states client-purchased equipment excluded — reconcile £23.25M process line at Concept.

## Slide 6
Direct Works Breakdown
Works subtotal £41,968,226
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Chart: 
| Process equipment (works lin | Building services (HVAC/MEP) | External works | Superstructure | Substructure | Internal finishes | Facilitating / enabling | Works to existing building | Fittings & equipment
GBP | 23249083 | 9532716 | 1859520 | 3942636 | 1499680 | 1270672 | 254960 | 204000 | 154960
Process equipment (works line 5.6): £23,249,083 (55.4%)
Building services (HVAC/MEP): £9,532,716 (22.7%)
External works: £1,859,520 (4.4%)
Superstructure: £3,942,636 (9.4%)
Substructure: £1,499,680 (3.6%)
Internal finishes: £1,270,672 (3.0%)

## Slide 7
Contingency & Risk Allowance (Feasibility)
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Design development (15%): £7,748,149
Construction & equipment risk (25%): £12,913,581
Client contingency (10%): £5,165,433
Risk register (factored): £626,600
Combined risk & contingency provisions are material (~33% on top of base construction plus other costs) — appropriate for Stage 1 OOM, subject to drawdown governance.
Pre-mitigation risk exposure (report §14.3): ~£2.64m cost / 182 weeks programme (factored lower).

## Slide 8
Investment Analysis — CFO Considerations
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Nature of estimate: Order-of-magnitude only; not for final Capex approval (cost plan disclaimer).
No escalation, inflation, FX, or tax in base date 22-May-2026.
Client-purchased process equipment stated excluded; process line £23.25M in works schedule requires reconciliation at Concept Design to avoid double-count or gap.
Excluded: client project management, operations, consumables, survey remediation beyond allowances.
Design fees included: £3,807,357 (8% of construction) — whole-project allowance, not FEED-only.
Accuracy improves at Concept (RIBA 2) with surveys, procurement strategy, and equipment quotes.

## Slide 9
Indicative Programme (Scitech Appendix 8)
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Feasibility study issued (RIBA 1): May 2026 [Complete]
Concept design (RIBA 2): Jul 2026 – Feb 2027 [Planned]
Scheme design (RIBA 3): Feb 2027 – Sep 2027 [Planned]
Planning consent (target): Mar 2028 [Planned]
Detailed design (RIBA 4): Oct 2027 – Jun 2028 [Planned]
Construction (RIBA 5): Aug 2028 – Nov 2029 [Planned]
Project complete (programme): May 2030 [Planned]
Risk register #13: desired Q3 2028 completion noted as tight vs master programme (construction through Nov 2029; project complete May 2030). Milestone definitions require alignment.

## Slide 10
Critical Decisions & Next 90 Days
Gate: Concept Stage Gate instruction to proceed — 16 Feb 2027 (programme)
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Approve Stage 2 Concept Design appointment (planned 1 Jul 2026).
Confirm Option 1 — hydrogenation building demolition/relocation.
Resolve ground-floor Hastelloy reactor headroom strategy (lower slab vs relocate).
Align internal completion target (Q3 2028 aspiration vs May 2030 programme).
Authorize pre-planning submission and long-lead equipment planning in Concept phase.

## Slide 11
Recommendation to Group Leadership
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
Support conditional advancement to RIBA Stage 2 with planning consent as external gate.
Budget planning: use £78.1M OOM as envelope for dialogue; hold separate provision for client-direct equipment and inflation until Concept cost plan issued.
Mandate procurement strategy workshop (risk #18) before major commitments.
Request Scitech stage-gated fee quote and cash-flow phasing for FY planning.

## Slide 12
Data Integrity & Limitations
Source: Scitech-EKIUM: 300291-RE-0001 Feasibility Report, 300291-CM-0001 Cost Plan, 300291-PM-PR-0002 Programme (May 2026)
All figures from published Scitech feasibility deliverables in repository (May 2026).
No RMB conversion or NPV presented — requires group FX and hurdle-rate policy.
Programme dates are indicative; Stage 2+ contract not included in this dataset.
For audit trail: 300291-RE-0001, 300291-CM-0001, 300291-PM-PR-0002, 300291-PM-RA-0001.