## Risk and Opportunities
ASYMCHEM G-128 ALTERATIONS CONCEPT ESTIMATE RISK REGISTER
High | [16 empty] | NET TOTAL OF ALL RISK & OPPORTUNITIES | [5 empty] | 397875 |  |  |  | Total Cost of Measures |  |  |  |  | #REF! |  |  | #REF!
Substantial
Moderate | [20 empty] | Low Est. | High Est. |  |  |  |  | Total of Risk to End Cost |  |  |  |  | 397875 |  |  | 397875 |  | No. of Risks | 12
Low | [16 empty] | ESTIMATED LIABILITY / OPPORTUNITY RANGE |  |  |  | 146632.6935 | 649117.3065
[27 empty] | Total of Opportunity to Reduce End Cost |  |  |  |  | 0 |  |  | 0 |  | No. of Opportunities | 0
CONFIDENTIAL FOR INTERNAL CIRCULATION ONLY
[5 empty] | Inherent Risk and Opportunity Rating |  |  |  |  | Current level of Risk and Opportunity Rating | [15 empty] | Initial Risk Rating |  | Residual Risk Rating |  | Statistical Variance | [5 empty] | Most Likely Estimate |  |  | Count | Opportunity or Risk
Risk / Opportunity ID | Date Raised | Risk or Opportunity | Description | Owner | Likelihood | Impact |  | Rating | Risk and Opportunity Strategy | Is there a residual risk or opportunity? | Is it now an opportunity or a risk? | Description / Mitigation Strategy | Mitigation / Implementation Measure Owner | Likelihood | Impact |  | Rating | Best / Lowest Cost | Likely Cost | Worst / Highest Cost | Most Likely Additional Cost or Cost Saving | Programme Impact | Active / Open / Closed | Date Closed | Comments | Tweak to allow blue 12 (actually 11.9 rounded) in col. K for S2/L4 | Normal score for col. F | Tweak to allow blue 12 (actually 11.9 rounded) in col. R for S2/L4 | Normal score for col. L | Average | Standard Deviation | Low - Variance from Average | High - variance from average | Risk Live? |  | Low - Variance from most likely estimate based on % deviation | RISK & OPPORTUNITY | High - Variance from most likely estimate based on % deviation
1 | 2026-08-02 | Risk | End user consultation | Employer | 2 | 3 | 12 | M | End Users might change their aspirations | Yes | Risk | Ensure the concept has been communicated to the client and end users, gaining their input and ensuring the project brief meets these requirements. | Employer | 2 | 3 | 12 | M | 80000 | 200000 | 400000 | 66000 |  | Open |  | Aug 26 - Have assumed (Best) = 2% increase, (Likely) = 5% increase, (Worst) = 10% increase in overall estimated construction and equipment costs of £4m | 24 | 12 | 24 | 12 | 226666.6667 | 131993.2658 | 94673.4008 | 358659.9325 | Yes |  | 27566.6667 | 66000 | 104433.3333 | 1 | Risk
2 | 2026-08-02 | Risk | Budget insufficiency | Employer | 3 | 3 | 15 | S | Fundamental difference in design or client change that the initial budget was based on compared to the initial design | Yes | Risk | Establish project brief as soon as possible and produce initial cost plan to ensure the project is financially viable. | Employer | 3 | 3 | 15 | S | 0 | 200000 | 400000 | 100000 |  | Open |  | Aug 26 - Have assumed (Best) = no change, (Likely) = 5% increase, (Worst) = 10% increase in overall estimated construction and equipment costs of £4m | 45 | 15 | 45 | 15 | 200000 | 163299.3162 | 36700.6838 | 363299.3162 | Yes |  | 18350.3419 | 100000 | 181649.6581 | 1 | Risk
3 | 2026-08-02 | Risk | Cost certainty | Employer | 3 | 3 | 15 | S | Completeness of design | Yes | Risk | Look to obtain a fixed lump sum cost from a Contractor on a Design and Build Procurement strategy to ensure cost certainty once design evolved. | Employer | 3 | 3 | 15 | S | 0 | 0 | 0 | 0 |  | Open |  | Aug 26 - The cost plan assumes a fixed lump sum price based on a D&B procurement route. The risk, if any, will be realised in Trade Contractor procurement, see risk 5 | 45 | 15 | 45 | 15 | 0 | 0 | 0 | 0 | Yes |  | 0 | 0 | 0 | 1 | Risk
4 | 2026-08-02 | Risk | Design changes | Employer | 3 | 3 | 15 | S | Design development | Yes | Risk | Ensure estimates are robust and adequate contingency is available. Furthermore, early design coordination will benefit any potential unforeseen design clashes. | Employer | 3 | 3 | 15 | S | 0 | 95000 | 190000 | 47500 |  | Open |  | Aug 26 - Have assumed (Best) = no change, (Likely) = 5% increase, (Worst) = 10% increase in estimated construction and equipment costs provided by the contractor of c.£1.9m | 45 | 15 | 45 | 15 | 95000 | 77567.1752 | 17432.8248 | 172567.1752 | Yes |  | 8716.4124 | 47500 | 86283.5876 | 1 | Risk
5 | 2026-08-02 | Risk | General completeness of design | Employer | 3 | 3 | 15 | S | Trade Package design is incomplete or details are unintentionally missed due to pressure during build up to tender period or some items are unknown at this stage due | Yes | Risk | Defer trade package procurement until detailed design complete | Employer | 3 | 3 | 15 | S | 0 | 0 | 95000 | 11875 |  | Open |  | Aug 26 - The concept programme assumes Trade Contractor procurement commences based on a complete detailed design. This particular risk is therefore limited. If the programme is expedited and Trade Contractors quote on the basis of the co-ordinated design then this risk should be re appraised. | 45 | 15 | 45 | 15 | 31666.6667 | 44783.4295 | -13116.7628 | 76450.0961 | Yes |  | -4918.7861 | 11875 | 28668.7861 | 1 | Risk
6 | 2026-08-02 | Risk | Contractor shortage | Employer | 3 | 3 | 15 | S | Inability to find sufficient interested and capable contractors/ subcontractors to tender | Yes | Risk |  | Employer | 4 | 3 | 18 | S | 0 | 0 | 0 | 0 |  | Open |  | Aug 26 - Potential that there are insufficient Trade Contractor returns to confirm pricing is competitive. Contractor & WC would need to benchmark returns. | 45 | 15 | 72 | 18 | 0 | 0 | 0 | 0 | Yes |  | 0 | 0 | 0 | 1 | Risk
7 | 2026-08-02 | Risk | Damage outside of the site demise | Employer | 3 | 3 | 15 | S | Damage to existing structures through demolition/removal of material from site | Yes | Risk | Contractor at site setup must ensure adequate protection to all items not within the project and the surrounding area including the route to and from site for waste removal / operatives. | Employer | 3 | 3 | 15 | S | 0 | 0 | 0 | 0 |  | Open |  | Aug 26 - An allowance has been included within the cost plan for the Contractor to protect common areas. Any damage would be a Contractor liability. | 45 | 15 | 45 | 15 | 0 | 0 | 0 | 0 | Yes |  | 0 | 0 | 0 | 1 | Risk
8 | 2026-08-02 | Risk | Excessive unplanned noise, dust nuisance levels | Employer | 3 | 3 | 15 | S | The project and building occupants are subject to excessive unplanned noisy works | Yes | Risk | Times when noisy works can take place will need to be advised by client before tender documents are released. Mitigation will entail weekend / out of hours working | Employer | 3 | 3 | 15 | S | 0 | 0 | 25000 | 3125 |  | Open |  | Aug 26 - The Cost Plan anticipates that forming openings and demolition of walls will need to be completed out of hours. There remains a risk that is a worst case scenario some work is delayed or incurs a further premium to be completed out of hours. | 45 | 15 | 45 | 15 | 8333.3333 | 11785.113 | -3451.7797 | 20118.4464 | Yes |  | -1294.4174 | 3125 | 7544.4174 | 1 | Risk
9 | 2026-08-02 | Risk | Extended equipment delivery timescales | Employer | 3 | 3 | 15 | S | Manufacture and delivery timescale in excess of 12 weeks | Yes | Risk | Confirm and place equipment orders as soon as practical | Employer | 3 | 3 | 15 | S | 0 | 40000 | 100000 | 22500 |  | Open |  | Aug 26. The cost plan assumes roughly a 3 month manufacture / deliver period. Potential that this could be 5 to 8 months for Isolators delaying the commencement of works on site, or the in ability to complete work if works have commenced. Assume costs of £20k/mth although likely these could be mitigated. (Best) = no delay, (Likely) = 2mths, (Worst) =5 mths. | 45 | 15 | 45 | 15 | 46666.6667 | 41096.0934 | 5570.5733 | 87762.76 | Yes |  | 2685.8121 | 22500 | 42314.1879 | 1 | Risk
10 | 2026-08-02 | Risk | AHU dilapidated or insufficient for requirement | Employer | 3 | 3 | 15 | S | Replacement of AHU required / work over and above allowances within cost plan | Yes | Risk |  | Employer | 3 | 3 | 15 | S | 200000 | 250000 | 300000 | 125000 |  | Open |  | Aug 26 - Have assumed (Best) = £200k, (Likely) = £250k, (Worst) = £300k increase in estimated construction costs | 45 | 15 | 45 | 15 | 250000 | 40824.829 | 209175.171 | 290824.829 | Yes |  | 104587.5855 | 125000 | 145412.4145 | 1 | Risk
11 | 2026-08-02 | Risk | Physical access for installation of new equipment | Employer | 3 | 3 | 15 | S | Equipment URS doesn't adequately consider equipment constraints. | Yes | Risk | Check access dimensions and ensure these ae correctly stated in equipment order. | Employer | 3 | 3 | 15 | S | 0 | 0 | 25000 | 3125 |  | Open |  | Aug 26 - Have assumed (Best) = no cost, (Likely) = no cost, (Worst) = £25k increase in estimated construction costs to remove walls and rebuild openings if necessary. | 45 | 15 | 45 | 15 | 8333.3333 | 11785.113 | -3451.7797 | 20118.4464 | Yes |  | -1294.4174 | 3125 | 7544.4174 | 1 | Risk
12 | 2026-08-02 | Risk | New Fume Cupboards required | Employer | 3 | 3 | 15 | S | Estimate assumes existing fume cupboards can be re-used, but condition has not been confirmed | Yes | Risk | Check condition of fume cupboards | Employer | 3 | 3 | 15 | S | 0 | 0 | 150000 | 18750 |  | Open |  | Aug 26 - Have assumed (Best) = no cost noting allowance in cost plan, (Likely) = no cost, (Worst) = £150k increase to purchase new fume cupboards if necessary | 45 | 15 | 45 | 15 | 50000 | 70710.6781 | -20710.6781 | 120710.6781 | Yes |  | -7766.5043 | 18750 | 45266.5043 | 1 | Risk
[7 empty] | 0 | [8 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Yes |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | [8 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Yes |  | 0 | 0 | 0 |  | 0
[36 empty] | 146632.6935 | 397875 | 649117.3065
Note on F12: The Risk or Opportunity Rating before any mitigation/maximisation measures have been taken.
Note on K12: The Risk and Opportunity Rating after any mitigation/maximisation measures have been taken.
Note on W13: (Y / N) Choice
Note on X13: Active - Risk is live and is actively managed. Open - Risk is live and managed via day to day management practice and procedures Closed - Risk mitigated or no longer an issue

## Matrix
Risk is assessed by first assigning a value to each of the Likelihood and the (most likely) Severity of the risk event, according to the definitions below:
|  | L1 | L2 | L3 | L4 | L5
Likelihood |  | Remote: May occur in freak/exceptional circumstances | Unlikely: Could occur but doubtful | Possible: Uncommon but known to occur here | Likely: Likely to occur | Highly Likely
Wouldn’t be surprised if… |  | There was no credible sign of it occurring | It occurred elsewhere but not here | It occurs | It occurs a couple of times | Common or repeating experience
|  | 0 - 10% chance | 10 - 30% chance | 30 - 50% chance | 50 - 75% chance | 75+% chance
Risk price weighting assumption (Amend % to alter calaculation / test senstivity of 'Most Likely Additional Cost or Cost Saving' on Risk Register) |  | 10% | 30% | 50% | 75% | 90%
|  | S1 | S2 | S3 | S4 | S5
| Category | Insignificant | Minor | Serious | Severe | Catastrophic
(most likely) Severity | Financial loss (unplanned) | £5k - £20k | £20k - £50k | £50k - £500k | £500k - £1.0m | > £1.0m
| Programme Delays | < 2 weeks | 2 - 4 weeks | 5 - 8 weeks | 9 - 16 weeks | > 16 weeks
| Safety/Injury | 1st aid injury; No lost time | Injury/illness requiring minor professional intervention; Self-cert lost time | Injury requiring hospital stay; Some irreversible damage; Reportable; Lost time < 2 weeks; Regulator improvement notice | Major or permanently disabling injury (PDI)/severe chronic illness; Lost time > 2 weeks; HSE or equivalent enquiry; Regulator prohibition order | Fatal injury/illness; Multiple PDIs; Large no. of victims; Police investigation
| Reputation | Occasional negative comments locally; Occasional biased local press reporting; Complaints by small group of stakeholders | Adverse local media attention; repeated complaints by customers; groundswell of lack of local confidence | Mobilisation of action groups; Repeated adverse local media attention; Some negative national coverage Sustained lack of influential confidence | Major customer intervention; Local govt/ govt agency policy change; Persistent adverse national media attention; Widespread boycott | UK/EU govt intervention or major stakeholder withdrawal with strategic effect; Adverse intl. media attention; Chronic hatred by interest groups
For functional/individual risks, the register will then automatically calculate the overall risk score and allocate a risk aversion colour code, as follows:
Likelihood -------------------------------------->
Severity -----------> |  | L1 = (1 + 2) = 3 | L2 = (2 + 2) = 4 | L3 = (3 + 2) = 5 | L4 = (4 + 2) = 6 | L5 = (5 + 2) = 7
| S5 = 5 | 15 | 20 | 25 | 30 | 35
| S4 = 4 | 12 | 16 | 20 | 24 | 28
| S3 = 3 | 9 | 12 | 15 | 18 | 21
| S2 = 2 | 6 | 8 | 10 | 12 | 14
| S1 = 1 | 3 | 4 | 5 | 6 | 7
As you can see, each value of Likelihood has been increased by 2; this is intentional and has the effect of weighting the register in favour of those risk events whose consequences have a greater (most likely) Severity.
For example, a risk event of Severity 1 can only score 7 (blue), even with a maximum Likelihood of 5.
A risk event of Severity 5, however, will always score at least 15 (amber), even with minimum Likelihood of 1.