# AI润色

A: So, meeting she’s having with, uh, sounds like a project meeting for the... Okay, uh, presume our Venus. He’s just finishing; that should be down in a moment.

B: She is.

A: Hello.

B: Hi, June.

A: Morning.

B: Yeah, great.

A: I’m not sure. Was he calling or coming here?

B: I don’t know. I don’t think you invited him.

A: Welcome to this list.

B: Oh, don’t invite any.

A: But I intended to.

B: Then I was invited.

A: Uh, Claire, Dave, remember that.

B: No, I have invited him, but it doesn’t show on others invited on the list. It’s on my, it’s on my...

A: He’s on the attendee list.

B: Yeah, attendee list.

A: I was gonna say, oh, that’s not going on here. But to be fair, I have done that before. I realize somebody hasn’t turned up because I haven’t invited them.

B: Hey, here he is.

A: Here he is.

B: They were just telling me off for not inviting you. But I’ll show you the list on here.

A: Doesn’t show that you’re invited.

B: Yeah.

A: No, not shown on the list. Not shown on the list on the screen here. But on the, uh, invite is definitely not accept the invitation.

B: Well, yeah, I think it doesn’t really get...

A: So I’ll let you get your coat off before I start. And we got 30 minutes and then we do another meetings.

B: Yep.

A: Yeah, I’ve got loads to do, so it will be very wait.

B: So we have the information through from Nicole, um, and including our equipment that we need to purchase. It’s coming out around four and a/2 5, depending on what we put in tolerances, or how comfortable we feel with the numbers.

A: I think Hong Jay had been asked to have a look at whether there was anything that they thought was missing. Is that correct? I just wanted to follow up to see where we were with that assessment and agree what the next steps were for this particular project.

B: So for Dave’s benefit, Dave was wasn’t here last week. So we’ve done some work with Woodley Cole, who are quantisaving team on site. So they have been round the lab, and we’ve had some discussions with them around what they would need to, where we would need to make modifications to the lab. We’ve got some cost from suppliers for isolators in the UK, and we’ve got a price list from guys in your team for the equipment that would need lab to make it a working lab. So with all that work, we’ve got an approximate value for the program.

A: Um, it’s now what do we do with those numbers? Those numbers don’t include any additional costs associated with staffing the projects; they’re just the capex side of the costs. That will be the question: what do you want to do around, what do we need to include for overhead to manage and execute this program?

B: So does the number include any kind of EPCM contractor types?

A: So they’re their program type.

B: I’ll pull it up in a minute. Their program timeline includes the assumption that we’re going to work with sitec and then take the approximate cost from previous work that we’ve done with sitec.

A: So as we discussed with Woodly calls, kind of discovery part doing the execution, but sitec doing design.

B: Well, that’s what we’ve got to work out. So at the moment, I think we have sitec also doing the execution because it changes the liability piece with the program, of who’s response, well, if we find issues. So if we take, do a design with an EPC, and then we take that and give that to a third party, if there are issues, then it becomes difficult to resolve and it tends to increase additional costs. So I think the cost at the moment assume the EPC are then gonna manage site and the third party contractors as well. There are different ways of doing it, and then we can work that out. We’ve concluded the EPC because that generally is that is the higher cost, but is the lower risk. So there’s a risk appetite discussion that we need to have as well about, but we don’t need to do that now. But there’s a piece before we get too far into the program, we need to have an understanding of what level of risk the organization wants to take through the program, around how we structure who is doing what work and who is responsible and what the contracts would need to look like with various people. I would advise that we, as we go into contracts for this, that we do buy some more time from Woodley Cole to help us to make sure the contracts are what we’re expecting.

A: But the question is, is sitec capable of doing EPC?

B: Yes, yeah, yeah, yeah. Sitec should be the people we use because they have all the original, they do have a construction team or, or they do have some, uh, contractor to work

A: Yes, yeah, yeah, yeah. They did all the work. They did all the work, Pfizer. So they were like the last people to work in that space. So when Pfizer exited, Sitec were already working in that lab on a program. We can get a, or from Sitec, we can see the differences between the EPC and EPCN and then see how much they were actually add up. I haven't, I haven't, EPC, I haven't, I've got a quote. I haven't progressed anything else because I wasn't quite sure.

B: This is why we're having a discussion of what you want to do next. We've got an order of magnitude number now, which should be a top end number, ish.

A: Yes, it should be. You know, because there's a lot of equipment cost in there. There is. And a lot of necessarily all need to be done initially. But no, a lot of cost is also around isolate purchase.

We also need to agree what we think those isolators are going to achieve, because if we want to go down to the lower end of AUB5, that limits all options in terms of places where we can purchase equipment. Talking to a couple of suppliers, they recommend there's only two or three people based in the UK who can achieve those levels. I have tried to work with some of the Chinese manufacturers, but the information we've got back has been that they tend to specialize in bespoke rather than off-the-shelf units.

So we need to work through whether there is anybody who can supply from China who will be cheaper than what I've got currently. So I've spoken to Tofflon and I've approached some other...

B: So which Chinese vendors have you been... Um, and, and, and the list is provided by Hongjie, or the list is provided by the EHS team?

A: At the start of the year, they provided a list of, I see, recommended suppliers who'd be able to supply into the UK and meet UK regulations. So I've approached some of them. Some were easier, some I got nothing useful back at all. They just sent me a brochure, so it's not off the shelf. If they're not off the shelf, we'd have to spend time and effort with them to do a design before even getting a price.

It's built into the overall program of the lab, so there's opportunities to reduce the timeline depending on the purchasing decisions we want to make. But ultimately, there's two decisions: are we going to go ahead, and what work do you want to buy up prior to getting that decision? Because at the moment, there's a lot of estimated cost. They're good estimates because Woodley Coal do this for a living, so they have a good understanding of what other projects on site have cost.

So working with Sitec, they've got an understanding of what that looks like. So they have costed some of that for us from their previous experience. But it would be good to understand if Ponjee has done some work, what was his findings, and how did that compare to what we've got from Woodley Coal.

我们这边这个正在是安排的这个事情，但是现在还没做出来。最近确实是在国内都在做这个 VOA 的相关的事情，呃我估计下周可能能拿出相关的一个国内的费用测算来。

B: Did you get it?

A: No, ha ha ha ha ha ha ha ha.

C: Ha, ha, ha, ha, ha, ha, ha, ha, ha, ha, ha.

A: So, I think they are doing a lot of that's fine. Yeah, yeah, but it's just whether we spend a lot of resource, because I just joined the conference call yesterday and they did give us a big feedback that we're not very good in terms of doing all the standards of maintaining the BLA qualification. So I think they spend a lot of time to upgrade our facilities.

So he said it is under way and the result will come out next week.

B: Okay. And are we gonna wait for that? So what is the plan for looking for funding for this? What is our approach, and what else do you need from us?

A: I think we can go in parallel, right. We actually can see this 4.5 million as kind of a ceiling. What do you think?

B: It's a business risk, isn't it. And I'm going to say, who's going to do that or where's that resource coming from? And combined with the retrofit of a ground floor, it's about what, seven point something million, right? So it's roughly about 12 million.

I can't remember what number we got to in terms of pounds.

A: Yeah, yeah, it's all pounds.

B: Yeah, it's all pounds.

A: Yeah, yeah, it's seven something.

B: Yeah, yeah, in dollars.

A: Uh, no, no, no, it's all pounds. It's all pounds.

B: Yeah, yeah, yeah, because we all use pounds here. Do you remember the retrofit of ground floor, 7 point something?

A: Right.

B: It was about that, because it ended up being about ten and a half million dollars.

A: Yeah, could not remember the exact number.

B: Oh, in here. In here.

A: Oh, yeah, the phone number.

B: Yeah. So, yeah, C1, lie off, lies a prep HCL C&C 1. It's about 7.

A: Seven and a half.

B: Yeah, it's close to 12, I think around. Yeah, with the numbers over there, the 7 point something for, 7 point something plus with the additional. So we got 4, four and a half, 5 form from, uh, we plan to do the lifelizer and then we added some additional work costs associated with C1 upgrades.

A: And then we've got, then there's also can, can you find the file?

B: Can, so you, I think you, you got the file right. You got the summary.

A: Yeah.

B: Can you share that one?

A: Yeah, I I'm looking for that.

B: How many projects we can support from the high pot lab, this time current, we respect it for four reactions.

A: Four reactions.

B: Yeah, for different steps.

A: Yeah.

B: What we need to agree though is we need to agree, when we're gonna write, we need to write scope of what OVD, we think this lab is going to achieve, and what the actual measure level limits are we going to achieve, because that changes significantly the specification of the equipment we need to buy. So if we don't have that agreement upfront, we will end up spending a lot of time and potentially money having to do changes to the program. Or we will build something that isn't good enough and we still won't be able to execute programs, which time will be.

A: So if you go if you go back to your page 2, I think, Peter, page 2.

B: This one.

A: Let's go to page 2.

B: You got it listed out as three things, I think it's 7.8 something, right?

A: Yes.

B: Yeah. Go to page 2.

A: Page 2.

B: Yeah, going back.

A: Yeah, not this one.

B: This is extension.

A: Yeah, don't go extension. Yeah, page 2.

B: Uh, you're on page six. You're going the wrong way.

A: Uh, okay, except to, to this one 5.33 for the HPLC and why is it 2.48 for C1?

B: Right, and then you need to add your, that would be 5 lab onto that, right, right. So this, uh, uh, remember that the 7 point something.

A: Yeah, it costs 12 then it is to, P C s d N C.

B: Based on this uh, cost it over 7.8 million pound but we can handle that.

A: We be seeking to, well, that's what we need to agree because we, we haven't agreed the absolute spec and scope for that, uh, upgrade.

B: Yeah, so, so the C1 module thing there so the 2.48, then whichever page there's a summary page Peter, of everything that's included in that. So that did include two new isolators.

A: We've since done the occupational.

B: Yeah, yeah. We've done the occupational health exposure monitoring the existing isolator, and it just achieves OEB5, but it won't do down to OEB6, which isn't an official category and we didn't do all the operations on that isolator.

A: No.

B: So it'll do, it'll do your standard OEB5 type stuff, but you want to go to ADCs, it won't satisfy. So you need to keep all the money in.

A: Uh, or we can do a extra layer of Protection for OEB6 because we already standardized the design by OEB5.

B: If there's still some gap, then we still can the, case by case doing some uh project evaluation need to be realistic, that that first round of industrial hygiene testing we did a very select amount of testing, so we haven't covered the full range of operations. So we do need to come back and do that.

A: I think we should leave the money.

B: Yeah, if you stick to that number that would, that would give you a new isolator which you could design.

A: And normally if, if we buy uh, IOC Dover, I, I'm very confident that at the end we probably can achieve OEB6.

B: And that's what, uh, we, uh, we're looking, even we giving them the spec is OEB5, but I think their design, they will give more buffer with the more safety factor.

A: And we have got designs and cost in back from IOC Dover to upgrade the outlet of the f of the FDA, Two, to put a continuous liner on the outlook port where we currently discharge CTC's, And we've got some information on putting, uh, free sand isolators around the charge point valves which we need to be able to achieve the OB six.

B: Okay, so we need to just check against the assumptions that were made in that number.

A: They're not bad pricing.

B: I don't haven't seen the assumptions that went into that number. So I think if you get if you go further through, it's got them listed

A: Okay, Peter, can you send me a copy of this slide deck, please?

B: Yeah, sure. No problem.

A: 7.8, right?

B: Yeah.

A: And if we add another 4.5 for hypolab, so it's somewhere between 12 to, uh, 13 million, right?

B: Yeah, it's 12.3.

A: Yeah. And then if you want to do that into dollars, it's about 16.6.

B: Hmm.

A: The 4.5 meaning for the high, for the lab, to which level of the OEB?

B: For equipment, we calculate OEB 5 or OEB 6.

A: I was confused.

B: Well, it's specified, but we've tried to, we are working with people who can achieve lower levels of OEB 5. Normally, I think in the lab, because the handling quantity is small and the duration is short, you can lower one layer of the containment, so achieve that hypothesis. So normally if you can achieve one, you can say it already is OEB 5.

A: Yeah, but it's different in the manufacturing, and also cover the material below on the line.

B: Yeah, potentially, yeah.

A: I think it's no problem, you know, but we have to just agree. But that's what we're trying to achieve because when we have the spec for one, we need to cover the material below point 1.

B: Is there any significant cost?

A: No, but it will probably change who we can work with because, from discussions with manufacturers, some of them are less confident they can achieve the bottom end.

B: Yeah, be fine.

A: So we go to a rely like that. She's talking about we go to good manufacturers, then the controls will be actually that we can achieve lower. If we go to some of the people who do it less frequently, you may, that's I'll sell you something that achieves OEB 5, but it will just, uh, at the bottom line. But if you, uh, I'll, uh, I'll see double if you tell him we want to achieve point one, they will supply you point zero one.

B: Yeah, exactly.

A: This is what the differences of the supplier. The manufacturer have different approach.

B: So, okay.

A: But I also don't work because the premium, yeah, cost, yeah. So it's like a 12.3 million, yeah, if we like to cover over the six.

B: Um, hmm.

A: There could be some cost increase, but based on the situation, probably not. Shouldn't be huge.

B: Yeah.

A: Okay. I think that's your number. That should give you everything.

B: So inflation is the one thing that moves things quickly as well. Inflation and availability will be the other piece. We may need to pay more to get things quickly if that's what, if you want short timelines, we may need to pay premium to get ahead of the queue.

A: Yeah. So for the half the lab we can handle for project or for reactions?

B: For reactions, yes. Not for projects. We never scripted for four projects. You need a different size lab for that. Probably two projects.

A: That's easy in the isolator.

B: Yeah. So some of it isn't, some of it isn't. It's a bit like the lab in not putting everything, not every activity in that whole space will be in isolators, just in the main room, and you'll get, it was basically four big isolators and one small isolator. Powder handling is an isolator, where it's a liquid and we're doing reactions, that will be in walking few birds.

A: Uh-huh.

B: But it was in a suite with a dedicated extract area so that we don't have to put lots of controls around the general labs, that's causing issues for routine operation. It makes it easier for the people actually working in there in terms of it's only precise things that they, uh, when you talk about price increases, so I had a notification yesterday from Emerson, so, you know, and this will be quite similar, right, in the procedures. It depends on how many, uh, segregation for, for, uh, different, uh, reactions we still can handle for, for different parts because in the lab it's not GMP.

A: No, it's not.

B: No, it's not GMP. So don't worry about the so-called cross contamination. But we have to make sure that protection for the people is sufficient. It's only 200 square meter. It's, to me, it's a very small area.

A: Yeah, 215, right, 1 2, 2, 1 1 five.

B: Yeah. And one of the things we will need to reality check is we can actually get all that equipment in the space. So the area is not very big in terms of overall material flow or

A: Personnel flow, because it's going to designing the lab again, in terms of as a number to add it to this. The intent when we put this document together was that then yourselves would be discussing, with the rest of the senior leadership teams in Tianjin, okay, what's going to progress. How are we going to actually get to making a decision to progress any or all of these things?

So, you could basically, on this overview, add a fourth line to put the OAB5 Labs onto it. And then, as Peter's already done in terms of each of the rest, you go behind it. Basically, each of those three lines has got three or four slides saying what's the key elements of the scope, what's the key costings, what's the program. And one thing to note: your timings need to include where the milestones need to move, because we haven't started.

Yeah, this was from Duke. 2030 probably doesn't need to change, but the lyophilizer doesn't need to reflect that we've taken a delay.

B: Um hmm.

A: Because the lyophilizer was the overall rate-determining factor of the delivery. The prep HPC could be done quicker, but now can't be done by September next year probably.

B: No, it's never started. We need to start in June.

A: Yeah. And what do you want to include in terms of staffing and headcount associated with these programs?

B: You mean during the design and engineering phase?

A: There's two elements, isn't there? There's design and engineering, and then operation and execution.

B: Um, um.

A: Does that need to be part of this presentation, or is that something we're going to agree separately? Because that's still going to be a cost to the program.

B: I think we need the ROI.

A: Yeah, yeah. How about the rate for the high port labs? We would like to charge.

B: Ha ha, after you reach, yeah, something like that.

A: Uh, how about, all right, I mean you would normally do some kind of benefit and cost-benefit analysis to understand how many years you're going to have to, what your payback is. So your projects would normally have to achieve a hurdle, right?

B: Yeah, and that's actually what we're talking about: three projects altogether, right?

A: Yeah, yeah. If you take us to one, you've got three listed there, but the top ones, the extension of the whole building, extensions, and like we're talking about Hyperlab and the HPLC, lyophilizer in the C1 module.

B: Well, you need to, we still see C1 probably need to come together.

A: Yeah. So they're one project in reality, although we costed them slightly. I mean, in terms of workload, it's more legacy projects in the, uh, yes, yeah, yeah. We can handle under one umbrella, but I think it's actually separated out there because we were saying that you'll see in my own would be done with external resource predominantly, but C1 was the one we felt we might be able to manage better in house. But that's still, yeah, yeah, you still got to resource it.

So that's why I'm thinking about it, that we do need more engineering resource for handling this. And it's not just engineering 2 + 1 projects. We need to think about what other roles also will require some resource to support this as well. And if you want to layer on the other projects we've been talking about recently, around revitalizing the cryogenic system and then upgrading a loop reactor, then we need to do a more systemic review, because it won't just result in one place. We need to look at them as a whole of what you're going to execute through this time frame. We're actually looking to start quite a lot of programs in one go, so we do need to look at the overall resourcing and the relative priorities, and get agreement and alignment on that input.

B: The, like how many resources we need to support the three projects we can pull up together? Do you need that as for the presentation? How many resources, how long it will take for that?

A: Yeah, I bear in mind it'll be approximate, but it'll be a starting point.

B: Yeah, yeah.

A: So we can have the idea of if we need the recruitment for the additional resources, or we can have the resource internal to support that.

B: We don't have resources.

A: Yeah, yeah. So this is why we need the, this is, yeah.

We have that breakdown. There was, in terms of taking out the extension, the others, and then along with lab over here, an expectation that there was at least two, and probably more like three process or project engineers, with a view that they would then initially work on this and then be kind of in the organization, delivering some of the other stuff subsequently as well.

But if you want to do other projects as well, yeah, yeah, other headcount that's needed in different roles. Yeah, this one is an example: HPLC, low flow, laser, and C1 in here. It's very light touch in terms of impact onto the DCS, just a few signals coming back and forth. That's about it.

But then if we want to do getting the loop reactor back up, that's a huge amount of time with a DCS engineer, because there's coding to write, software to write, that was never transferred onto Delta V, and laybacks, and similar for the cryo. Yeah, and the same for the cryo. So then if Simon's taking up doing that, his day-to-day needs to be covered by us. And at the moment, there are others that can do all of the day-to-day that we need. It needs a more holistic view.

But we need to have some understanding of roughly what we think we want to do for the next 18 months, two years, and then we can work out where the resource gaps might be. But certainly, we can pull some resource in together for these programs, for executing the delivery of them.

Peter, can you put the information similar like this for the hype for the lab, uh, summarize in this slide, share with the team?

A: Yeah, sure. I can put together what we got.

B: Dave, I know we've talked around you. Have you got any questions?

C: Sorry, I think Peter was trying to talk, but he was on mute.

A: Yeah, yeah, yeah. I can put together what we got, uh, the current information into this, and, uh, no problem.

B: Okay. And in the similar, uh, similar module or similar style.

A: Um, hmm.

B: Okay. So have you got any questions?

C: No. Just to say, I guess, maybe reinforcing what you were saying, Claire, we do need to make sure we've just got to prioritize what we want to do because we can't do it all. So what we're going to tackle first, does it make sense to tackle a lab first and then work out how we resource that? My understanding with the optimizer was the priority.

A: Okay. It all depends in terms of based upon the lead times as well and when we want something. But in terms of, even though delivery of HPLC and lufaizer was scheduled for after the lab, to get it to deliver even by then, you need to start it first.

C: Hmm.

A: That's the kind of difficulty. So it's back to when, when do we want things available? And then we can work backwards from there.

C: Exactly. Start on first and it's understanding what the business driver is, which one do we actually want first.

A: Yeah, yeah, because starting anything at the moment is stopping something else until we get some more headcount. The leader will summarize the hype of the lab in the slides and then maybe need your support to get the resources to yeah, this project.

C: So if I don't get to it tomorrow, it'll be another week because I'm on holiday.

A: It's okay.

C: Yeah. So, uh, question maybe later we can talk about how about our right, um, support the this investment.

A: Yeah. Anything you, I know you said another meeting now. Is there anything else we need to cover now, just on that engineering resource, Claire, would we bring contractor in to do to support that? Is that what you think you would propose? Or would we bring an FTE in?

C: Uh, it depends. So if, uh, how much is working with a third party, if it's working with a third party, it's better with an FTE because then you have an FTE managing a contractor. There's challenges with having contractors managing contractors.

A: Yeah, so the how we structure the programs will decide whether we, and to be fair, we may have no choice but to bring a contractor in, given how difficult finding just to get started.

C: Yeah, a contractor could be.

A: So we might be able to bring a contractor in to pick up some of the other projects to allow to keep, for example, to move on to supporting some of this.

C: Yeah, but we need

A: We need to, we need to, we need a clear plan of how we're gonna do that. Contractors all come with a level of overhead that an FT doesn't from a management and work planning point of view.

B: Okay. All right, thank you.

A: So, so, I've heard the only thing I need to do in the short term is provide you some resources, and I'm not gonna carry with anything else in the short term. Is that correct?

B: Um, hmm, yeah. Yeah. Resources from you and Peter, organize everything in a slide.

A: Yeah, you may need to send some information to Peter. You've got a copy of that from the, uh, he's already got it in the same format as what's needed in the rest of this. He's got copy. He's got access to all the files I've got from will call already.

B: Yeah, okay, so this, but that, that he's looking at, I think this was sent in an email to us on the 12th of June.

A: Okay, that probably was that. I was in holiday.

B: Yeah. So you can see what sort of stuffs there in there, because it might, it might only take you five minutes to summarize it for him too.

A: Yeah, to be clear, we're not progressing anything else at the moment.

B: They're on hold until you tell me to do something else.

A: All right, thank you very much.

B: Okay. Two weeks later, we can submit the proposal. Thank you. Thank you. Thank you. Thank you.

A: Are we gonna go next door for the next meeting with Dave and, uh, with, do you wanna hang up?