## Slide 1
Asymchem UK · Sandwich PDF capital projects
1 / 31
Internal briefing
Asymchem UK · Sandwich Pilot Plant
Capital projects briefing
1. Ground floor and C1 upgrade
£7.81M
HPLC + lyophiliser £5.33M C1 Oct 2027 / HPLC Dec 2027 / lyophiliser Jun 2028
2. OEB5 high-potency laboratory
£3.55M
Phase 1 basis (excludes Phase 2 equipment) Target delivery November 2027
3. B902 east extension
£78.1M
Feasibility OOM Completion May 2030
Briefing date: 12 October 2026

## Slide 2
Asymchem UK · Sandwich PDF capital projects
2 / 31
Portfolio overview
Three parts · feasibility / concept / internal estimate
Workstream | Scope | Investment (order of magnitude) | Key date
1. HPLC + lyophiliser | Retrofit within the existing PDF footprint (ground floor) | £5.33M | HPLC Dec 2027 / lyophiliser Jun 2028
C1 module OEB5 upgrade | Routine OEB5 operation of the existing C1 module | £2.48M | Installation and qualification, October 2027
2. OEB5 high-potency laboratory | Alteration of the existing G-128 suite; GIFA 215 m²; 4 + 1 isolators | £3.55M (Phase 1) | Target delivery November 2027
3. B902 east extension | New four-storey building with a plant mezzanine: reaction, hydrogenation, filtration and drying | £78.1M | Completion May 2030
Linked delivery: the in-building retrofit (preparative HPLC and lyophiliser) and the C1 upgrade have to finish together before preparative HPLC can run at OEB5. The preparative HPLC unit sets the overall delivery timeline.
Demand basis: European BD has compiled the high-potency demand and opportunities directed at Sandwich (2027–2030). Named accounts are AZ, Genmab, BioNTech and NCC. Roche, Innovent and MediLink have also enquired about overseas high-potency capacity.
Parts 1 and 2 together (retrofit £5.33M + C1 £2.48M + high-potency laboratory Phase 1 £3.55M, excluding Phase 2 equipment) are about £11.36M, excluding the B902 east extension. Each line rests on a different estimate basis: the extension and the retrofit are feasibility level, C1 is an internal estimate, and the high-potency laboratory is a concept cost plan.

## Slide 3
Asymchem UK · Sandwich PDF capital projects
3 / 31
High-potency, purification and lyophilisation demand · accounts and projects
Account | Project | Status | 2027–2030 volume | BD value basis | Notes
AZ | Exatecan（ASYM-128214） | Lost | 43.2 kg | $5–6M | Enquiry of September 2025. GMP payload-linker awarded to the European supplier Procos (Italy). Non-GMP manufacture remains at Pharmaron Ningbo. Launch expected no earlier than 2030. A second-source opening may be pursued from H2 2028.
AZ | ADC linker AZ14374332 (ASYM-147285, Exatecan as intermediate) | Lost | 37 kg | $18M | Same as the row above
AZ | AZD5305（ASYM-124995） | Live · second source | TBD | — | Seven-step synthesis, the last two steps high-potency. Sandwich holds a process-optimisation PO and is running it in the laboratory. AZ has not given a commercial volume. If Sandwich adds high-potency capacity, a second-source position is available to pursue.
AZ | Camizestrant / AZD9833（ASYM-147692） | Live · second source | ~8,800 kg | $5-10M/yr | The final step is high-potency. Current supply is Cambrex US. The kilogramme figure is estimated from annual intermediate demand, not an API order confirmed by AZ.
AZ | Other ADC programmes | Enquiry | — | — | AZ has a broad ADC payload-linker pipeline and has recently asked to understand the Sandwich high-potency expansion plan.
Genmab | LD038.TFA（ASYM-129959） | Live · second source | 71.8 kg | $86M | Payload-linker. BLA filing planned for the end of 2026. Tianjin has completed PPQ and commercial batches are in progress. The customer is assessing a US/EU second source and is watching the Sandwich expansion plan. A collaboration would require a further upgrade of BLA capability.
BioNTech | BNT3214（ASYM-139154） | Live · transfer to Sandwich | 8 kg | $15–20M | Early work is currently supported from China. The intention is for Sandwich to take the long-term supply once the project moves forward.
NCC | Exatecan mesylate | Requirement listed | 6 kg（2027） | TBD | Only 6 kg is listed for 2027. Later years and the value are TBD.
Roche / Innovent / MediLink | Enquiry on overseas high-potency capacity | Enquiry | — | — | All three are asking about overseas high-potency capacity.

## Slide 4
Asymchem UK · Sandwich PDF capital projects
4 / 31
High-potency, purification and lyophilisation demand: customers are asking about capacity
Compiled by European BD · Sandwich high-potency demand and opportunities (2027–2030)
4 named accounts
AZ · Genmab · BioNTech · NCC
3 enquiries
Roche · Innovent · MediLink (no volume)
2 opportunities lost
AZ Exatecan + linker GMP
Asked about the expansion
AZ and Genmab have both asked about the Sandwich plan
European BD has listed the high-potency demand and opportunities directed at Sandwich.
Named accounts are AZ, Genmab, BioNTech and NCC. Roche, Innovent and MediLink have also enquired about overseas high-potency capacity.
AZ and Genmab have explicitly asked to understand the Sandwich high-potency expansion plan. For several projects the ask is a US/EU second source, to hedge supply risk.
BioNTech wants to extend a programme now supported from China into Sandwich, and has set out the capability required: high-potency containment comparable to TJ4 (1 ng/m³), laboratory through kilogramme scale, fit-for-purpose high-potency chromatography, high-potency lyophilisation, and high-potency analysis segregated from routine analysis.
Containment and HP analysis
BioNTech requires containment comparable to TJ4 (1 ng/m³) and high-potency analysis segregated from routine analysis. This maps to the G-128 high-potency laboratory.
High potency, chromatography and lyophilisation
The same account lists fit-for-purpose high-potency chromatography and lyophilisation. This maps to the in-building HPLC and lyophiliser retrofit.
Second-source window
AZ Exatecan drug-linker and the AZD5305 project
Genmab plans to file the BLA at the end of 2026. Tianjin is already in commercial manufacture, and a US/EU second source is under assessment. Several AZ APIs are likewise framed as second-source opportunities.

## Slide 5
Asymchem UK · Sandwich PDF capital projects
5 / 31
Part 1
1. Pilot-plant ground floor and C1 OEB5 upgrade
HPLC + lyophiliser (RBPC FS P01) · C1 module OEB5 upgrade (internal estimate)
£7.81M
Part 1 investment
£5.33M
HPLC + lyophiliser
£2.48M
C1 OEB5 upgrade
2028-06
Latest milestone (lyophiliser)

## Slide 6
Asymchem UK · Sandwich PDF capital projects
6 / 31
Part 1 · investment and milestones
HPLC, the lyophiliser and the C1 OEB5 upgrade are delivered together, and together they provide OEB5 operation of preparative HPLC.
Item | Investment | Build-up | Key date | Basis
HPLC + lyophiliser | £5,329,100 | Direct £3,026,800 + indirect £1,072,500 + 30% project contingency £1,229,800 | HPLC Dec 2027; lyophiliser Jun 2028 | RBPC FS P01
C1 OEB5 upgrade | £2,476,500 | Main equipment £1,905,000 + 30% project contingency £571,500 | Installation and qualification, Oct 2027 | Internal estimate; supplier budget quotations
Total | £7,805,600 | of which project contingency £1,801,300 | — | —
Principal equipment
• Lyophiliser £967,000; HPLC skid £358,000
• Fixed isolators £1,000,000; flexible isolators £330,000
• HVAC and airlocks £575,000
Linked delivery
• The C1 upgrade completes before HPLC is brought into use (Oct 2027, then Dec 2027)
• Lyophiliser manufacture, at 8–10 months, is the critical path for Part 1
Contingency basis
• Both lines carry a 30% project contingency
• £1,801,300 in total. HPLC + lyophiliser also carries 30% price risk

## Slide 7
Asymchem UK · Sandwich PDF capital projects
7 / 31
HPLC + lyophiliser · executive summary
9802-RBP-ZZ-ZZ-RP-X-100000
Technically feasible
FS P01
£5.33M
Total investment estimate
2027-12
HPLC target (+3 months)
2028-06
Lyophiliser target (+3 months)
• Scope: preparative HPLC (DAC300/CP300) plus a lyophiliser (isolator, dehumidification, pure-steam generator and associated items) and the supporting retrofit.
• Investment: total CAPEX estimate £5.33M (direct + indirect + 30% project contingency). This is not the final Capex.
• Programme: driven by the long lead time of the lyophiliser. The lyophiliser is procured ahead of the HPLC.
• Dependency: delivery has to stay in step with the C1 OEB5 upgrade, otherwise preparative HPLC cannot run at OEB5.
• Demand link: on the European BD list, BioNTech names high-potency chromatography and lyophilisation as capabilities required for a long-term move to Sandwich.

## Slide 8
Asymchem UK · Sandwich PDF capital projects
8 / 31
HPLC + lyophiliser · scope
HPLC
• DAC300/CP300 pump skid; mobile head tanks; 2,000 L waste tank
• Costed on a Hanbon (China) basis
• Installed in area PG.05
Lyophiliser
• Lyophiliser chamber, isolator, dual CIP, dehumidification, PSG
• Costed on a Tofflon basis
• Airlock and retrofit, about 20 weeks

## Slide 9
Asymchem UK · Sandwich PDF capital projects
9 / 31
HPLC + lyophiliser · investment
9802-RBP-ZZ-ZZ-CP-X-100001
Total investment estimate
£5,329,100
Direct costs | £3,026,800
1. Main process equipment | £2,047,500
1.1 Lyophiliser | £967,000
1.2 HPLC skid | £358,000
1.3 Tanks and vessels | £200,000
1.4 Pumps | £50,000
1.5 Price risk (30%) | £472,500
2. Infrastructure retrofit | £979,300
2.1 Civil and structure | £326,000
2.2 Mechanical and piping | £264,000
2.3 Electrical and instruments | £128,000
2.4 HVAC | £35,300
2.5 Price risk (30%) | £226,000
Indirect costs | £1,072,500
3. FEED study | £225,000
4. Detailed design | £289,000
5. CDM | £235,000
6. Commissioning | £76,000
7. Price risk (30%) | £247,500
General risk and contingency | £1,229,800
Project contingency (30%) | £1,229,800

## Slide 10
Asymchem UK · Sandwich PDF capital projects
10 / 31
HPLC + lyophiliser · investment structure
Direct / indirect / general risk and contingency
£5,329,100
Total investment
£3,026,800
Direct costs
£1,072,500
Indirect costs
£1,229,800
General risk and contingency
1. Main process equipment £2,047,500
2. Infrastructure retrofit £979,300
Total investment build-up
Chart: 
| Total investment
Direct costs | 3026800
Indirect costs | 1072500
General risk and contingency | 1229800
Direct costs by item
Chart: 
| Lyophiliser | HPLC skid | Tanks and vessels | Pumps | Civil and structure | Mechanical and piping | Electrical and instruments | HVAC
£ | 967000 | 358000 | 200000 | 50000 | 326000 | 264000 | 128000 | 35300

## Slide 11
Asymchem UK · Sandwich PDF capital projects
11 / 31
HPLC + lyophiliser · programme
FS §4.4 Figure 1 · re-baselined to a September 2026 start (June basis + 3 months)
Lyophiliser manufacture
8–10 months
HPLC supply
~18 weeks
FEED
12–14 weeks
Detailed design
18–20 weeks
2026 H1
2026 H2
2027 H1
2027 H2
2028 H1
FS / baseline
2026/05 – 2026/05
Engineer mobilised
2026/09 – 2026/10
FEED (indicative)
2026/10 – 2027/01
Detailed design (indicative)
2027/01 – 2027/06
Lyoph spec / funding
2026/09 – 2026/11
Lyophiliser manufacture
2026/11 – 2027/08
Lyoph FAT
2027/08 – 2027/09
Lyoph ship and install
2027/09 – 2027/12
Lyoph validation to PQ
2027/12 – 2028/06
HPLC spec / funding
2026/12 – 2027/02
HPLC manufacture
2027/02 – 2027/06
HPLC FAT
2027/06 – 2027/07
HPLC ship and install
2027/07 – 2027/09
Mobile head tanks
2026/11 – 2027/08
Waste tank
2026/11 – 2027/08
Retrofit
2027/04 – 2027/08
Today
Done
Procurement / manufacture
Construction / qualification
Critical path
Engineer mobilisation
§4.3 indicative

## Slide 12
Asymchem UK · Sandwich PDF capital projects
12 / 31
C1 · executive summary
Routine OEB5 operation of the existing C1 module
Routine OEB5 operation
Upgrade objective
£2.48M
Total investment estimate
2027-10
Installation and qualification (+3 months)
• Scope: fixed isolators for material dispensing on the upper floor and final packing on the ground floor; HVAC upgrade; interlocked inlet and outlet airlocks with a mist shower; custom flexible isolators covering each unit operation and the waste streams.
• Estimate: budget quotations are in hand. ILC Dover, flexible isolator for reactor charging, £115,800 for the package, including concept design of the R19–R22 charging arrangement. Howorth, single-chamber dispensing isolator, £250,000 each. Both are ex works and exclude packing, transport, installation and commissioning.
• Selection: this is an upgrade of the existing facility, with local alterations rather than installation of a complete new machine, so a China-sourced isolator is not recommended. Every part placed in the UK has to meet UK standards and carry the CE mark; retrospective certification adds at least 3–4 months, and the extra cost and time are not a good trade.
• Linked delivery: it has to finish with the in-building retrofit (preparative HPLC and lyophiliser) in order to give preparative HPLC an OEB5 operating capability.
• Programme: assumed to be approved together with the retrofit. The preparative HPLC unit drives the C1 delivery timeline.

## Slide 13
Asymchem UK · Sandwich PDF capital projects
13 / 31
C1 · scope
Fixed isolators
• Upper floor (second floor): material dispensing
• Ground floor: final packing
HVAC and airlocks
• HVAC upgrade to support routine OEB5 operation
• Interlock upgrade on the inlet and outlet airlocks, including a mist shower
Flexible containment
• Several custom flexible isolators
• Covering each unit operation in the module, and the waste streams
Pricing basis (supplier quotations)
• Flexible isolator: ILC Dover JS26-11384-0 (22 July 2026), £115,800 for the package, EXW, excluding transport and installation; about 20 weeks after drawing approval
• Fixed isolator: Howorth Q26543 (11 August 2026), single-chamber dispensing isolator £250,000 each; options of a 190 RTP at £18,000 and a mock-up at £17,000

## Slide 14
Asymchem UK · Sandwich PDF capital projects
14 / 31
C1 · isolator selection
A China-sourced isolator is not recommended
CE mark required
Condition of UK placement
+3–4 months
Minimum for retrospective certification
Off-the-shelf high integrity
The type this project needs
• Anything placed in the UK has to meet UK standards and carry the CE mark. The China-sourced option does not currently carry CE.
• Retrospective CE marking adds at least 3–4 months on the experience of other projects, and longer if certification requires design changes.
• The design and test documentation that CE marking requires was not prepared against that standard, so assembling it is a substantial piece of work.
• This project needs an off-the-shelf high-integrity isolator. Information received from the China suppliers approached has not been usable as it stands. Tofflon mainly builds isolators bespoke to a piece of equipment, which is not this requirement.
• Recommended route: develop the supply on the Howorth and ILC Dover budget quotations already in hand.

## Slide 15
Asymchem UK · Sandwich PDF capital projects
15 / 31
C1 · investment
Internal estimate · main equipment + 30% project contingency
Total investment estimate
£2,476,500
Main equipment (equipment and design) | £1,905,000
1. Fixed isolators | £1,000,000
1.1 Upper floor (second floor), material-dispensing fixed isolator | £500,000
1.2 Ground floor, final-packing fixed isolator | £500,000
2. HVAC and airlocks | £575,000
2.1 HVAC modification and upgrade | £350,000
2.2 Airlock interlocks and mist shower | £225,000
3. Flexible containment | £330,000
3.1 Custom flexible isolators for each unit operation | £330,000
General risk and contingency | £571,500
Project contingency (30%) | £571,500

## Slide 16
Asymchem UK · Sandwich PDF capital projects
16 / 31
C1 · investment structure
Main equipment subtotal / project contingency
£2,476,500
Total investment
£1,905,000
Main equipment subtotal
£571,500
Project contingency
Total investment build-up
Chart: 
| Total investment
Main equipment subtotal | 1905000
Project contingency | 571500
Main equipment by item
Chart: 
| 1. Fixed isolators | 2. HVAC and airlocks | 3. Flexible containment
£ | 1000000 | 575000 | 330000

## Slide 17
Asymchem UK · Sandwich PDF capital projects
17 / 31
C1 · programme
Assumes approval together with the retrofit · re-baselined to a September 2026 start (June basis + 3 months)
Scope freeze
8 weeks
Detailed design
12 weeks
Order and manufacture
20 weeks
Installation and qualification
8 weeks
2026 H2
2027 H1
2027 H2
Scope freeze
2026/10 – 2026/12
Detailed design
2026/12 – 2027/03
Order and equipment manufacture
2027/03 – 2027/08
Installation and qualification
2027/08 – 2027/10
Today
Design / preparation
Order and manufacture
Installation / qualification

## Slide 18
Asymchem UK · Sandwich PDF capital projects
18 / 31
Part 2
2. OEB5 high-potency laboratory (G-128 suite alteration)
Concept stage · cost plan 6 Aug 2026 / concept programme 27 Jul 2026 / risk register
Concept stage
Cost plan / concept programme / risk register
£3.55M
Phase 1 investment estimate (excludes Phase 2 equipment)
2027-11
Target delivery (concept programme + 6 weeks)
215 m²
GIFA (laboratory c. 182 + write-up c. 33)

## Slide 19
Asymchem UK · Sandwich PDF capital projects
19 / 31
High-potency laboratory · executive summary
DPH_G-128 Suite Alterations Concept Cost Plan 260806
Concept stage
Cost plan / concept programme / risk register
£3.55M
Phase 1 investment estimate (excludes Phase 2 equipment)
2027-11
Target delivery (concept programme + 6 weeks)
215 m²
GIFA (laboratory c. 182 + write-up c. 33)
• Scope: alteration of the existing G-128 suite into laboratory and write-up space, GIFA 215 m². The cost plan allows isolators at 4 × £150,000 + 1 × £100,000.
• Investment: Phase 1 project investment including inflation is £3,550,444, VAT excluded. The full figure including Phase 2 and later equipment is £4,300,044.
• Build-up: building works £1.95M + professional services £0.14M + Phase 1 owner equipment £0.96M + risk allowance £0.40M + inflation £0.10M.
• Programme: the draft concept programme is 262 working days from funding approval and the decision to proceed, with delivery targeted for November 2027. Isolators arrive on 14 July 2027.
• Isolator cost: currently an estimate based on discussion with suppliers. The final figure depends on the containment level confirmed with the scope.
• Owner equipment is in two phases. Phase 1 is the equipment required to start up, £963,445, and is included now. Phase 2 and later is the equipment for the full fit-out, £749,600, and is not included now. The two phases together are £1,713,045 to purchase.
• Demand link: European BD has listed demand or enquiries from AZ, Genmab, BioNTech, NCC and others for high-potency capability at Sandwich. BioNTech specifically requires containment comparable to TJ4 and segregated high-potency analysis.

## Slide 20
Asymchem UK · Sandwich PDF capital projects
20 / 31
High-potency laboratory · scope
From the G-128 concept cost plan
Scope and area
• Alteration of the existing G-128 suite (G128 and G128A–D); GIFA 215 m²
• Laboratory about 182 m² (the basis of the services rates) + write-up about 33 m² (carpet quantity)
• Remove the blockwork wall between G128 and G128D; form 2 transfer-hatch openings and 2 door openings in the concrete wall
Isolators and laboratory equipment
• Cost plan: 4 × £150,000 + 1 × £100,000 (£700,000 in total)
• Nature of the cost: an estimate based on discussion with suppliers; the final figure depends on the containment level confirmed with the scope
• Fume cupboards: assumed to remain serviceable, with £20,000 allowed for servicing and repair. Whether to buy new is still open on the programme
• SF6 leak testing £20,000. Furniture covers lockers, a step-over bench, mobile benches and BIBO bins
Building and finishes
• Strip-out: clear furniture and laboratory equipment, remove floors and ceilings, and remove gas, ductwork, electrical services, smoke detectors and Crowcon
• New work: 475 m² of wall lining, 40 m² of new partition; 5 single-leaf and 1 leaf-and-a-half hygienic door, 2 timber doors, and 4 existing doors refurbished
• Finishes: 173 m² of laboratory sheet vinyl, 173 m² of metal ceiling, 33 m² of write-up carpet
Services, safety and owner supply
• HVAC £217,920: return the AHU to service, full supply and extract ductwork, bag-in/bag-out HEPA extract filtration, BMS upgrade and system balancing
• Electrical £107,380, sprinklers £30,030, access control / cabling / CCTV / fire alarm £51,345, laboratory gas pipework £63,700, mist shower £35,000
• Equipment supplied and installed by the owner (Asymchem): Phase 1 £963,445 (phased list, £1,713,045 to purchase in total)
• Phase 1 by group: ARD/QC £662,600, instruments inside isolators £175,345, CRD £125,500
Risk and premise: landlord consent for the alteration is being sought from DPML. Once altered, the laboratory cannot be handed back to DPML in its current operating condition, and Clare is following that discussion. DPML (Paul Bax, 21 August 2026) has agreed in principle to the proposed PDF and DPH alterations, including G.128, subject to design review. Two Licences for Alteration can be started, with scope and drawings added as the design develops.

## Slide 21
Asymchem UK · Sandwich PDF capital projects
21 / 31
High-potency laboratory · phased owner equipment
Equipment List Costs for scoping 0911
£963,445
Phase 1 equipment (included now)
£749,600
Phase 2 and later
£1,713,045
To purchase, total
£3,550,444
Phase 1 investment (incl. inflation)
Phase 1 · equipment required to start up
• Opening fit-out: one analytical HPLC bought first; the mass spectrometer and its gas supply are in Phase 1
• Instruments for solids handling inside the isolators are in Phase 1
• Reaction systems sized for one project at a time (one EasyMax, and similar items, bought first)
Phase 2 and later · equipment for the full fit-out
• Preparative HPLC, particle sizer and auto titrator
• Crystallisation screening, part of the reaction ancillaries, and glasswash
• Software £200,000, carried as later
Group | To purchase | Phase 1 | Phase 2 and later
ARD / QC | £832,600 | £662,600 | £170,000
Instruments inside isolators | £383,345 | £175,345 | £208,000
CRD | £497,100 | £125,500 | £371,600
Total | £1,713,045 | £963,445 | £749,600

## Slide 22
Asymchem UK · Sandwich PDF capital projects
22 / 31
High-potency laboratory · investment (1/2)
G-128 Concept Cost Plan · 2026-08-06 · GIFA 215 m²
Phase 1 investment (incl. inflation)
£3,550,444
Total building works estimate | £1,951,140
1 Facilitating works | £65,567
1.1 Strip-out, alterations and demolition (partitions and the like) | £46,967
1.2 Services strip-out (gas, ductwork, electrical, detectors, Crowcon) | £18,600
2 Superstructure | £68,690
2.7 Internal walls and partitions (wall lining, new partitions, hydrogen pipework boxing) | £42,440
2.8 Internal doors (5 single-leaf + 1 leaf-and-a-half hygienic, 2 timber, 4 refurbished) | £26,250
3 Finishes | £58,898
3.1 Wall finishes (laboratory 475 m², write-up 70 m²) | £9,810
3.2 Floor finishes (sheet vinyl 173 m², coved skirting 136 m, carpet 33 m²) | £23,631
3.3 Ceiling finishes (metal ceiling 173 m², perimeter detail 136 m) | £25,457
4 Fittings, furnishings and equipment | £765,000
Isolators, 4 nr × £150,000 | £600,000
Isolators, 1 nr × £100,000 | £100,000
Fume cupboards (existing assumed serviceable; servicing allowance only) | £20,000
SF6 leak testing | £20,000
Furniture (lockers, step-over bench, mobile benches, BIBO bins) | £20,000
Write-up furniture | £5,000
5 Services | £537,574
5.6 HVAC (AHU back into service, full ductwork, bag-in/bag-out HEPA, BMS upgrade, balancing) | £217,920
5.8 Electrical (small power 182 m², lighting 182 m², including equipment connections) | £107,380
5.4 Water (hot and cold, sink reinstatement, mist shower £35,000) | £38,600
Facilitating and building works subtotal | £1,495,729

## Slide 23
Asymchem UK · Sandwich PDF capital projects
23 / 31
High-potency laboratory · investment (2/2)
G-128 concept cost plan · continued
6 Preliminaries, including contractor design | £362,500
6.1 Temporary works (protection of retained equipment and common areas, temporary lighting) | £10,500
6.2 Site welfare and accommodation (21 weeks) | £21,000
6.3 Design and construction management (surveys, RIBA 2/3 and RIBA 4 contractor design, RIBA 5 site resource for 22 weeks) | £331,000
7 Overheads and profit (5.00%) | £92,911
8 Professional services | £141,800
Project management (33 weeks pre-contract / 22 weeks post-contract / defects), design support, commercial support and contract administration | £141,800
9 Equipment supplied and installed by the owner (Asymchem) | £963,445
Phase 1 equipment (phased list, included now) | £963,445
Phase 2 and later equipment £749,600 (not included now) | —
10 Risk allowance | £397,875
10.1 Design-development risk (per the risk register) | £397,875
11 Inflation (2.15%) | £96,184
Inflation from the base date through construction | £96,184
Phase 1 investment (incl. inflation) | £3,550,444

## Slide 24
Asymchem UK · Sandwich PDF capital projects
24 / 31
Equipment supplied and installed by the owner (Asymchem)
ARD / QC
This group, to purchase £832,600 · Phase 1 £662,600
Phase 1 total £963,445
Item | Location | Manufacturer | New / existing | Phase | To purchase | Phase 1
HPLC system | Room 2 | Aglient Technologies | New | Phase 1 | £200,000 | £100,000
HPLC/MS system | Bench top | Agilent Technologies | New | Phase 1 | £200,000 | £200,000
GCMS | or GCMS | — | New | Phase 1 | £120,000 | £120,000
Nitrogen generator | or GCMS | — | New | Phase 1 | £8,000 | £8,000
Hydrogen generator | or GCMS | — | New | Phase 1 | £8,000 | £8,000
Electronic pipette | Benchtop | Handystep | New | Phase 1 | £1,600 | £1,600
Milli-Q | Undersink | Millipore | New | Phase 1 | £20,000 | £20,000
Preparative HPLC | Large Fumehood | Hanbon (China) | New | Phase 2 | £70,000 | —
pH meter | Fumhood | Mettler Toledo | New | Phase 1 | £20,000 | £20,000
SFC | Bench top | Waters | Existing | Phase 2 | — | —
GC | Bench top | Aglient | Existing | Phase 2 | — | —
Mass spectrometer | Bench top | Aglient | New | Phase 1 | £140,000 | £140,000
Coulometric KF | Fumehood | Metrohm | New | Phase 1 | £45,000 | £45,000

## Slide 25
Asymchem UK · Sandwich PDF capital projects
25 / 31
Equipment supplied and installed by the owner (Asymchem)
Instruments inside isolators
This group, to purchase £383,345 · Phase 1 £175,345
Phase 1 total £963,445
Item | Location | Manufacturer | New / existing | Phase | To purchase | Phase 1
Huber TC45 with immersion cooler | Under isolator 2 | Huber | New | Phase 1 | £4,345 | £4,345
Auto titrator | Isolator 1 | Mettler Toledo | New | Phase 2 | £30,000 | —
Benchtop powder X-ray diffractometer | Bench top | D2 | Existing | Phase 1 | — | —
Particle sizer | Isolator 5 | Malvern | New | Phase 2 | £160,000 | —
Analytical balance | Isolator 1 | Mettler Toledo | New | Phase 1 | £20,000 | £20,000
Microbalance | isolator 1 | — | New | Phase 1 | £25,000 | £25,000
EasyMax reactor system | isolator 3 | Mettler Toledo | New | Phase 1 | £80,000 | £80,000
Chiller | under isolator 3 | Julabo | Existing | Phase 1 | — | —
Drying oven | Isolator 4 | Salvis | New / existing | Phase 1 | £36,000 | £18,000
FTIR | Isolator 2 | Thermo | Existing | Phase 1 | £28,000 | £28,000

## Slide 26
Asymchem UK · Sandwich PDF capital projects
26 / 31
Equipment supplied and installed by the owner (Asymchem)
CRD（1/2）
This group, to purchase £497,100 · Phase 1 £125,500
Phase 1 total £963,445
Item | Location | Manufacturer | New / existing | Phase | To purchase | Phase 1
Laboratory fridge | Room 4 | Lec | New | Phase 1 | £750 | £750
Laboratory freezer | Room 4 | Lec | New | Phase 1 | £750 | £750
Reactor Ready twin reactor | FH1 | Reactor Ready vessels | New | Phase 2 | £20,000 | —
Mettler Toledo SP-50 dosing unit | FH1 | Mettler Toledo SP-50 Dosing units | New | Phase 2 | £1,600 | —
RX10 controller | FH1 | RX10 Controller | New | Phase 2 | £2,400 | —
Heidolph motor | FH1 | Heidolph Motors | New | Phase 2 | £1,600 | —
Reactor Ready stand | FH1 | Reactor Ready Stand | New | Phase 2 | £1,000 | —
Vacuum pump | FH1 | Vacuubrand | New | Phase 2 | £5,000 | —
Recirculating chiller | FH1 | Huber | New | Phase 2 | £23,000 | —
Analytical balance | Either/or | Mettler Toledo | New | Phase 1 | £20,000 | £20,000
Large-scale balance | Either/or | Sartorius | New | Phase 1 | £1,000 | £1,000
EasyMax reactor system | FH2 | Mettler Toledo | New | Phase 1 | £160,000 | £80,000

## Slide 27
Asymchem UK · Sandwich PDF capital projects
27 / 31
Equipment supplied and installed by the owner (Asymchem)
CRD（2/2）
This group, to purchase £497,100 · Phase 1 £125,500
Phase 1 total £963,445
Item | Location | Manufacturer | New / existing | Phase | To purchase | Phase 1
Chiller | FH2 | Julabo | New | Phase 1 | £24,000 | £12,000
Stem heating blocks | FH3 | Electrothermal | New | Phase 2 | £2,000 | —
Stirrer hotplate | FH3 | IKA | Existing | Phase 2 | — | —
Biotage | FH4 - Flexible | Biotage | New | Phase 2 | £12,000 | —
Rotary evaporator | FH4 - Flexible | Heidolph | New | Phase 1 | £6,000 | £6,000
Vacuum pump | FH4 - Flexible | Vacuubrand | New | Phase 1 | £5,000 | £5,000
Overhead stirrer | FH4 - Flexible | — | New | Phase 2 | £1,000 | —
Software (TBC) | Software | — | New | Later | £200,000 | —
Glasswash | Miscellaneous | Miele | New | Phase 2 | £10,000 | —

## Slide 28
Asymchem UK · Sandwich PDF capital projects
28 / 31
High-potency laboratory · programme
Asymchem Concept Programme_260727（DRAFT CONCEPT PROGRAMME）
262 days
Duration (working days)
2026-10-13
Funding approval and decision to proceed
2027-07-14
Isolators on site
2027-11-12
Target delivery (including programme risk)
2026 H2
2027 H1
2027 H2
Funding approval
2026/10 – 2026/10
Appoint consultants + BoD
2026/10 – 2026/10
Principal contractor tender and appointment
2026/10 – 2026/11
Contract award and mobilisation
2026/11 – 2026/12
Surveys and project controls
2026/12 – 2027/02
Laboratory design
2026/12 – 2027/04
CDM
2026/12 – 2027/09
Isolator procurement and manufacture
2027/01 – 2027/07
Fume cupboard procurement (TBC)
2027/01 – 2027/07
Laboratory furniture procurement
2027/01 – 2027/06
Trade contractor tender
2027/01 – 2027/05
Construction
2027/05 – 2027/09
Commissioning and handover
2027/09 – 2027/10
Programme risk allowance to delivery
2027/10 – 2027/11
Today
Design / contracts
Procurement / manufacture / allowance
Construction / commissioning
Programme note: the activities finish in late October 2027, and the remaining float sits in the programme risk allowance at the end, with delivery targeted for November 2027. As design develops, some activities can be overlapped and shortened. How far depends on how the remaining risk is treated and how much risk is acceptable.

## Slide 29
Asymchem UK · Sandwich PDF capital projects
29 / 31
Extension · assessment outcome
3. B902 east extension (assessment outcome) · Scitech RIBA 1 · 300291-RE-0001 · 22 May 2026 Issue A1
FS complete
RIBA 1
£78.1M
Project OOM
2030-05
Master-programme completion
• Scope: about 600 m² on the east side, four storeys plus a plant mezzanine, 10 reactors, a 2,500 L hydrogenation vessel, 3 filter-dryers and the utilities.
• Option: Option 1, demolish or relocate the existing hydrogenation building, and connect through to the lower floors of 902.
• Status: the feasibility study is complete. Completion is planned for May 2030, on the designer's master programme. A late start to RIBA 2 concept design would have to be absorbed within the stage.

## Slide 30
Asymchem UK · Sandwich PDF capital projects
30 / 31
Extension · investment
300291-CM-0001
Project OOM total
£78,108,089
Direct construction | £59,489,961
Site clearance and demolition | £254,960
Substructure | £1,499,680
Superstructure | £3,942,636
Internal finishes | £1,270,672
Fittings and equipment | £154,960
Building services | £9,532,716
Process equipment | £23,249,083
Works to the existing building | £204,000
External works | £1,859,520
Preliminaries (8%) | £3,357,458
Contractor overhead and profit (5%) | £2,266,284
Subtotal | £47,591,969
Contingency (25%) | £11,897,992
Other project costs | £5,077,946
Design team fees (8%) | £3,807,357
Surveys and investigations | £80,000
BREEAM | £150,000
Planning and statutory fees | £25,000
Subtotal | £4,062,357
Contingency (25%) | £1,015,589
General risk and contingency | £13,540,182
Whole-project contingency (25%) | £12,913,582
Risk register (probability-weighted total) | £626,600

## Slide 31
Asymchem UK · Sandwich PDF capital projects
31 / 31
Thank you
Asymchem UK · Sandwich · 12 October 2026
Asymchem UK · Sandwich PDF capital projects
31 / 31